ITEM NO. 47 (A-39)

- Name of the Project

Disaster preparation with respect to N.D.M.C. schools

S.H:- Construction of fire escape staircases and underground tanks for fire protection in NDMC area. (Construction of Fire escape stair cae for NDMC schools.)

- Name of the Department

Civil Engineering Department Zone – II

- Brief history of the Subject

The New Delhi Municipal Council is responsible for an area of 42.74 sq. kilometer. This area includes the seat of the Central Government, Rashtrapati Bhawan, Prime Minister’s office and residence, central government offices, foreign missions, residence of ministers, member of parliaments, diplomat and central government employees. In addition to providing basic amenities to its residents, the municipal council also ensures various social, cultural, educational and medical facilities specially to the government/municipal employees and other weaker sections of the society.

N.D.M.C has decided to construct fire escape stair cases and underground tanks in the existing school buildings from the fire prevention point of view. The scope of work is to be decided by FO cum NA exploring the locations of the staircase where only one staircase exist and underground tank for fire safety purposes according to norms prescribed by fire protection.

After due exercise, FO cum NA came to the conclusion that the work  of  disaster preparedness is to be carried out in the initial stage of 17 nos. schools for which the PE amounting to Rs 91 lacs was approved by the council. The work in some schools have already been completed and work in some school are in progress   and remaining work in 10 schools are to be done.

- Detailed proposal of the project

The architect department has proposed and EE (design) has been supplied with the design for

  - M.S. Steel staircase made of M.S. Channel, M.S. Girder, M.S. Chequered plates, M.S. Angle mounted on RCC footing.

Earlier tender were called.  In the first and second call tenders were rejected due to higher rate and poor response. This is the third call and tenders were opened after completing all the formalities through e-procurement system and opened on 1.4.2009.  In response 4 tender were received as per detail given below :-

| S. No. | Name of the Contractor | Amount Needed | Percentage |
| --- | --- | --- | --- |
| 1. | M/S Puja Construction Company | 88,52,095/- | 30.75% above |
| 2. | Sh. Navin Kumar Gupta | 94,45,736/- | 39.52% above |
| 3. | M/S Raghav Engineers | 1,11,94,690/- | 65.35% above |
| 4. | M/s K.B.G. Engineers | 1,14,97,622/- | 69.82% above |

M/S Puja Constructions Co. have quoted the lowest rate of 30.75% above the estimated cost of 67,70,086/- and tendered amount of Rs 88,52,095/-. The justification has been worked out by the planning division at 23.47% above the estimated cost  put to tender of Rs 67,70,086/-. The lowest rate quoted by M/S Puja Constructions Co. is on the slightly  on the  higher side, with the prior approval of the chairman dated 28.04.2009, negotiations were conducted  in the chamber of CE(C-II) on 30.04.2009. The contractor was called for negotiations and asked to reduce his rates and explained the following reasons in support of his actions:

- The rates of steel prices are fluctuating very much and also stated that there are possibilities for further increase in rates.  In the NIT, the provision of clause 10CA has also not been considered and will not get any benefit in the absence of this clause as there is possibility of increase in cost of steel prices.

- Electricity charges are considered huge, keeping in view the likely consumption of the electricity for the work.

After due deliberation and persuasion, the contractor offered a rebate of 1% (one percent) over his quoted rates. Considering these factors, the negotiated rates worked out to be 29.45% above the estimated cost of Rs 67,70,086/- and the tendered amount worked out to be 87,63,574/-.After considering the revised offer the percentage of quoted cost over the justified cost  of the tender comes to 4.84% above .

Considering all the above difficulties expressed by the agency, likely increase in cost of steel prices, direction of Hon’ble Supreme court of India for the completion of such works at the earliest, the requirement of quality control of India for different schools and the requirement of Delhi fire service. Due to urgency of work it is recommended that the revised offer of M/S Puja Construction Co. @ 29.45% above the estimated cost of Rs 67,70,086/- and negotiated tendered amount of Rs. 87,63,574/-  and which is 4.84% above the justified cost is  considered  workable and recommended for acceptance.

5.	Financial implication of the project

The tendered amount of the work is Rs. 87,67,574/- and this will be charge to head of account C.3.8 ( Xiii ) Sl. 3 at P/113 against which budget provision of Rs. 60.00 lacs exists in the current year budget book 2009-2010.

6.	Implementation of schedule with time limit for each stage including internal processing

6 ( Six ) month of the award.

7.	Comments of the Fianance department on the subject

( i )		File reveals  that planning had checked the justification at 20.03% above ( P-67/N). Subsequently on review, the same has ben checked to 23.60% above the EC after considering 3% for scattered work. In this context, it may be pointed out that as per OM No. DGW/MAN/169 dated 31.12.2008, contractor’s profit and overheads have been increased from 10 to 15% wherein contractor’s overhead has been increased from 2.5 to 7.5% on account of factors listed in the said OM. On the face of this CE ( C-II ) may bring his comments on record on the justifications for considering 3% element on account of scattered work.

(ii). 	Correctness of data, computations and information supplied.

(iii). 	All bidders whose bids have been opened fulfill eligibility criteria as stipulated in the NIT.

(iv). 	Due publicity to NIT has been given as per approved policy of NDlMc .

(v). 	CVC guidelines on the subject have been followed during the process of tendering.

8.	Comments of the department on the comments of Finance department

The clarification of the observation of  Finance department are as under :

As per O.M. No. DGW/MAN/169 dated 31.12.2008 by increasing contractor profit and over heads from 10 to 15% change has been make in the contractor profit @ 7.5% as applicable earlier whereas the contractor  overhead has been increased from 2.5% to 7.5% on account of following factors :-

- Cost of Engineering establishment deployed by the contractor.

- Cost of T&P and heavy machinery which includes tower crane,

Material hoists, excavators, vibrators and heavy machinery for road constructions.

- Cost of cleaner environment at site & labour welfare facilities.

- Cost of Quality Assurance set up enhancing testing lab.

- Cost of office set up including engagement of necessary staff for computerized billing etc.

- Cost of Earnest Money/performance Guarantee/security deposits.

- Other miscellaneous expenditure.

Therefore no extra cost is to be added in justification on account of various factors mentioned above.

In this case, the works are to be carried out in 22NO. different schools which are located I complete NDMC area for which extra  provision has been considered for scattered work in the justification.  The case was examined by planning and 3% has been allowed on this account.

- The data computation and information given as per norms.

- The bidders bid opened who fulfill the eligibility criteria as stipulated in the NIT.

- Due publicity  has been given as per norms.

- CVC guidelines have been followed while processing the tender.

9.	Legal implication of the project

Nil.

10.	Details of the previous council Resolution, existing law of Parliament and assembly on the subject.

Administrative approval and expenditure sanction of the P.E amounting Rs. 91 lacs for the work for Disaster preparedness with r/o to NDMC schools has been resolved by the council vide No. 21(A-32) dated 22.08.2007.

11.	Comments of the law department on the project

Nil

12.	Comments on the department on the comments of the law department

Nil.

13.	Certify that all Central Vigilance Commission (CVC) Guildelines have been followed while processing the case

Certify that Central Vigilance Commission guidelines have been followed while   processing the case.

14.	Recommendations

The case is placed before Council for acceptance of revised offer of L-I i.e. M/s Puja construction Co. at their revised  offer @ 29.45% above the estimated cost of Rs. 67,70,086/- with negotiated tendered amount of Rs. 87,63,574/- (Eighty seven lac sixty three thousand five hundred seventy four only)  which is 4.84% above the justified cost .It is recommended that revised A/A/ & E/S for Rs.1,28,89,845/- which is based on lowest quoted rate and expenditure incurred be accorded. It is also recommended that permission be accorded the with the work in anticipation of approval of minutes of the Council.

15.	Draft Resolution

Resolved by the Council that the negotiated offer of M/S Puja Construction Co. with negotiated tendered amount of Rs.87,63,574/- (Eighty seven lac sixty three thousand five hundred seventy four only) i.e 29.45 % above the estimated cost of Rs. 67,70,086/-  is accepted along with revised Administrative Approval and expenditure sanction Rs.1,28,89,845/-and department may initiate action in anticipation of confirmation of the minutes of the Council.

COUNCIL’S DECISION

Resolved by the Council to accept the negotiated offer of M/S Puja Construction Co. with negotiated tendered amount of Rs.87,63,574/-, which is 29.45% above the estimated cost of Rs.67,70,086/-, along with revised Administrative Approval and expenditure sanction amounting to Rs.1,28,89,845/- for the work of Disaster preparation with respect to N.D.M.C. schools.  S.H:- Construction of fire escape staircases and underground tanks for fire protection in NDMC area. (Construction of Fire escape stair case for NDMC schools.)

It was also resolved that further action in the matter be taken in anticipation of confirmation of the minutes by the Council.