ITEM NO. 18. (A-65)

1.	NAME OF THE SUBJECT/  PROJECT;

Sub: Special repairs to buildings in BM-PK division.

SH: Repair to water proofing of plaza level slab, expansion joint, main    		            	                 reception porch terrace and planters bed at Palika Kendra.

- NAME OF THE DEPTT./DEPTT. CONCERNED ;

Civil Engg. Deptt., NDMC.

- BRIEF HISTORY :

Palika Kendra building was constructed in the year 1983 – 84 .The water proofing work was also done during construction i.e.  Apx. 24 years before and, it has outlived its normal life span of 10 years. During last monsoon seepage was noticed through expansion joints, plaza slab, main reception porch terrace and planters bed etc. Existing filler in the expansion joints has lost its strength and need urgent replacement. The water seepage is further effecting the strength and quality of structure. The site was inspected by CE(C-II) with Sr. Officers and it was felt necessary to take urgent rectification measures. Leading and reputed firms, in the field of water proofing were approached for advising rectification measures. Experts of the firms inspected the sites and proposed latest and appropriate measures. Accordingly an estimate amounting to Rs. 55, 84, 849/- has been prepared based on expert opinion.

- DETAILED PROPOSAL ON THE SUBJECT / PROJECT :

An estimate amounting to Rs. 55, 84, 849/- has been framed based on expert opinion and is submitted to obtain A/A and E/S from the Council. The brief proposal is as under:-

  - Water proofing for plaza level slab with calendared high polymer water proofing membrane reinforced with polyester mesh and non woven needle punched polypropylene, G.O. textile 190 GSM over membrane as separation layer.

  - Water proofing for reception porch terrace with 4mm thick granule finish, APP modified bitumen water proofing membrane, reinforced by non woven polyester mat.

  - Expansion joints treatment for plaza level slab with PVC 1500 WMR over expansion joint. Expansion joints to be filled with fiber board and backing rod before laying membrane  and joint of membrane by hot air welding technique.

  - Water proofing of planter beds with calendared high polymer PVC water proofing membrane, having high resistance to algae and  route penetration

  - Sand stone / concrete  tile flooring on top surface.

- FINANCIAL IMPLICATIONS OF THE PROPOSED PROJECT/SUBJECT:

The total financial implication is of Rs. 55, 84,849/- and to be met against the provision for special repairs of buildings / extra ordinary repairs of buildings.

- IMPLIMENTATION SCHEDULE WITH TIMELINESS FOR EACH STAGE    	 	         INCLUDING INTERNAL PROCESSING :

The work will be completed within six months after awarding the work.

S. No.              Stage                                                               Target date.

1.            Preparation, scrutiny and T/S of D/E.                      31.01.2008

2.            Preparation of NIT, scrutiny in Planning and

Approval of NIT.                                                   15.02.2008

3.            Inviting tender & finalization                                   15.03.2008

4.           Completion of work after award                                15.09.2008

(Work is to be executed in the main movement

Area of officials and visitors. The work is possible

Only before and after office hours and on holidays)

- COMMENTS OF THE FINANCE DEPTT. ON THE SUBJECT :

We concur in the PE amounting to Rs. 55, 84,849/- as checked by planning at P-8/N against norms laid down for special repairs. According to the said norms, the amount for five years works out to Rs. 49,24,105/- ( flag-B) The remaining amount may be considered against “Extra ordinary repairs” and a proper account thereof be maintained for record purposed.

- COMNMENTS OF THE DEPTT. ON COMMENTS OF FINANCE DEPTT:

Keeping in view the advice of finance remaining amount will be considered against extra ordinary repairs and a proper accounts thereof  will  be maintained for record purposes

- LEGAL IMPLICATION OF THE PROJECT :

NIL

- DETAILS OF PREVIOUS COUNCIL RESOLUTIONS, EXISTING LAW     	   	         OF PARLIAMENT AND ASSEMBLY ON THE SUBJECT :

NIL

- COMMENTS OF THE LAW DEPARTMENT ON THE SUBJECT /PROJECT :

As no legal issue is involved, hence the matter was not submitted to Law department.

- COMMENTS OF THE DEPTT. ON THE COMMENTS OF LAW DEPTT:

Not required.

- RECOMMENDATION OF C.E. (C-II) :

The case is placed before the Council for approval of the proposal & to accord A/A and E/S to the preliminary estimate amounting to Rs.55, 84,849/- (Rs. Fifty five lacs eighty four thousands eight hundred forty nine only)

COUNCIL’S DECISION

Resolved by the Council to accord administrative approval and expenditure sanction to the preliminary estimate amounting to Rs.55,84,849/- for the proposed work.