ITEM NO. 16 (A-81)

1.	Name of  the Sub. 	:  Strengthening of Water Supply System in NDMC

Area.

Sub Head     	:  Construction  of  Water  Boosting  Station   at

Panchsheel Marg-Sardar Patel Marg Crossing.

- Name of the Deptt.	:  Civil Engineering, Public Health Circle, Water Supply

Division.

3.	Brief History of the Subject

NDMC is responsible for supplying potable drinking water in its jurisdiction to all its consumers.   Water is received in bulk from Delhi Jal Board and is further distributed through the network of approximately 450 k.mtrs. of main and distribution lines. As per study conducted by M/s Tata Consulting Engineers, the demand of water for NDMC Area is 225 MLD whereas DJB is supplying an average quantity of about 115 MLD based on monthly meter readings.   NDMC is generating about 10 MLD of water from its own 130 tubewells and thus there is a shortfall of about 100 MLD of water.

NDMC has constructed 23 Water Boosting Stations in its area and water drawn from DJB and generated through tubewells is collected in underground reservoirs and further boosted.  Further, two more water boosting stations viz.  I-Avenue and Nauroji Nagar have been constructed recently. However, presently, entire Chanakya Puri Area including I.B. Complex, all Embassies and Govt. Guests Houses are supplied water from Palam Reservoir of DJB through 27” dia (675mm) feeder main.  The Chanakya Puri Area is having lot of variation in ground levels and  Dhaula Kuan  and  Jesus & Merry College side  are at a higher level of about 7-8 metres. The water supply, as such, does not reach this area.  Consequent upon this, NDMC has installed an online 100 H.P. booster pump at Sardar Patel Marg - Panchsheel Marg on this 27” dia line for increasing the water pressure.  This booster pump exists there for the last about 30 years, however, DJB vide their letter dt. 8.8.05 (copy enclosed see page 75)  objected to  this online booster pump and the matter was brought to the notice of Hon’ble Chief Minister by CEO, DJB.  Though the Hon’ble Chief Minister was apprised of the position of online pump which was 2 km away from Palam Reservoir of DJB and the same runs for limited 2 hours in each shift by throttling the sluice valve, however, it was finally desired by the Hon’ble Chief Minister that some alternative arrangement may be made instead of putting an online booster pump.  Accordingly, proposal was earlier made to construct a water boosting station at Panchsheel Marg-Sardar Patel Marg Crossing for a capacity of 15 lac ltrs. and an estimate amounting to Rs. 2,80,32,900/-  was approved by the Council vide item No. 2(A-06) dt. 19.12.2007 for this scheme.  Since the proposed underground tank fell in R.O.W. of Panchsheel Marg, another suitable site was selected for construction of an underground tank in the park at Sardar Patel Marg  in front of Himachal Bhawan.  Since the site for construction of underground tank is a big park and keeping in view that DJB may increase the quantity of water in future and the work of interconnection of reservoirs may also be carried out for which A/A & E/S has been accorded by the Council separately, it has been decided to increase the capacity of the UGR from 15 lac ltrs. to 30 lac ltrs.  Consequent upon this, necessity of obtaining revised A/A & E/S has cropped up for which this revised estimate amounting to Rs. 8,04,66,500/-  has been framed.

4.	Detailed Proposal of the Subject :

The revised A/A & E/S estimate for Rs.8,04,66,500/- has been framed for construction of an underground tank for 30 lac ltrs. capacity and details of earlier approved estimate viz. a viz. proposed revised estimate are given hereunder :-

S.No.		 Sub Head 			Amount as per 	Amount as per 						earlier approved 	Revised Estimate.

Estimate.

i)	Construction of U/G tank 	 	Rs. 1,80,97,500/-	Rs. 3,93,98,400/-

ii)	Construction of Pump House		Rs.   13,96,462/-	Rs.    35,74,675/-

iii)	P/L Feeder & delivery  lines		Rs.    45,41,064/-	Rs.    23,38,7691/-

& shifting of existing lines.

iv)	Shifting of existing taxi stand (LS)	Rs.   2,00,000/-                    	NIL

v)	Shifting of tubewells (LS)		Rs.   2,00,000/-	         		NIL

vi)	Installation of pump set 	 	Rs.  27,81,287/-	Rs. 1,15,27,595/-

& connections including electric

external connections.

vii)	Leveling 				NIL 			Rs.       1,26,403/-

viii)	Horticulture operation 		     	NIL 			Rs.       1,08,017/-

Contingencies 3%			Rs,    8,16,489/-	Rs.      23,43,683/-

Total 			Rs. 2,80,32,900/-	Rs. 8,04,66,500/-

5.	Final Implications of the Proposed Subject :

The Revised Preliminary Estimate amounting to Rs. 8,04,66,500/- has been framed for obtaining administrative approval and expenditure sanction of the Council.   A provision of Rs. 100 lacs has been made in the revised budget proposals for the year 2008-09.

6.	Implementation Schedule with Timeliness for each stage including Internal Processing :

NIT for this work has already been processed and tenders will be invited thereafter.  The following time schedule will be implemented :-

a)	Call of Tenders 				-	1 Month.

b)	Award of Work 				-	3  Months

c)	Execution of Work 			-           9 Months

7.	Comments of the Finance Department on the Subject :

The  Finance Department  has observed as under :-

“Keeping in view the facts brought on record by the department that there would be sufficient source of water for proposed tank and technical soundness of work/tank which will further develop the infrastructure, we have no objection to the proposal of the department if the case for revised AA & ES amounting to Rs. 8,04,66.500/- (Rupees Eight Crore four lakh sixty six thousand five hundred only) is placed before the Council subject to correctness of information and following conditions :-

1.	Necessary NOC is taken from L&DO to avoid any dispute in future and to avoid wasteful expenditure due to any reasons/dispute on account of the title of land, before incurring any liability on the scheme.

2.	If required, necessary permission is obtained from Ministry of Environment/Forest.

3.	The scheme does not go against any plan/Scheme of MPD (Master Plan of Delhi).

4.	Since we do not find any approval/approval in principle/minutes of such decision of competent authority on record, the department may elaborate the necessity including optimum utilization of the tanks of proposed increased capacity in the draft agendum.

This issues with the prior approval of F.A.”

8.	Comments of the Department on Comments of Finance Department :

The comments of the Finance Department are clarified as under :-

1.	The proposed site for construction of UGR is a park being maintained by NDMC.  Titlewise, it is L&DO’s land and the matter will be taken up with L&DO for issue of NOC.

2.	No permission from Ministry of Environment/Forest may be required for construction of UGR.

3.	Since the proposed construction is in a park, it may not go against any plan/scheme of MPD.

4.	It has been decided in principle by the competent authority to construct UGR in this park.  Since the construction will be underground, the top will be maintained as a park again. The capacity of the underground tank has been increased so as to create infrastructure while quantum of water, in future, may be increased  by Delhi Jal Board.  Further, during interconnection of various reservoirs in NDMC area, this UGR may act as an important UGR for supply of water to areas for equitable distribution of water supply.

9.	Legal Implication of the Subject :

Not applicable

10.	Details of Previous Council Resolutions, Existing Law of Parliament and Assembly on the Subject :

Not applicable

11.	Comments of the Law Department on the Subject :

Not applicable

12.	Comments of the Department on the Comments of Law Department :

Not applicable

13.	Recommendations :

The case is placed before the Council for consideration and accord of revised administrative approval and expenditure sanction to the preliminary estimate amounting to Rs.8,04,66.500/- (Rupees Eight crore four lakh sixty six thousand five hundred only) for the above said scheme and to take up the work before issue of NOC by L&DO since the park is in possession of NDMC.

COUNCIL’S DECISION

Resolved by the Council to accorded revised A/A & E/S to the preliminary estimate amounting to Rs.8,04,66,500/- for the scheme C/o Water Boosting Station at Panchsheel Marg-Sardar Patel Marg Crossing. It was also resolved by the Council that the department may take up the work before issue of NOC by L&DO, since the park is in the possession of NDMC.