ITEM NO.02 (A-56)

1.	Name of  the Sub. 	:  Strengthening of Water Supply System in NDMC Area.

Sub Head     :   Construction  of  Water  Boosting  Station   at

Panchsheel Marg-Sardar Patel Marg Crossing.

- Name of the Deptt.	:  Civil Engineering, Public Health Circle, Water Supply

Division.

3.	Brief History of the Subject

Presently, entire Chanakya Puri Area including I.B. Complex,  all Embassies  and Govt. Guests Houses are supplied water from Palam Reservoir of DJB through 27” dia (675mm) feeder main.  The Chanakya Puri Area is having lot of variation in ground levels and  Dhaula Kuan  and  Jesus & Merry College side  are at a higher level of about 7-8 metres. The water supply, as such, does not reach this area.  Consequent upon this, NDMC has installed an online 100 H.P. booster pump at Sardar Patel Marg-Panchsheel Marg on this 27” dia line for increasing the water pressure.  This booster pump exists there for the last about 30 years, however, DJB vide their letters dt. 8.8.05 and dt. 20.08.05  objected to  this online booster pump and the matter was brought to the notice of Hon’ble Chief Minister by CEO, DJB during a meeting held on 18.08.05.  Though the Hon’ble Chief Minister was apprised of the position of online pump which was 2 km away from Palam Reservoir of DJB and the same runs for limited 2 hours in each shift by throttling the sluice valve, however, it was finally desired by the Hon’ble Chief Minister that some alternative arrangement may be made instead of putting an online booster pump.  Accordingly, proposal has been made to construct a water boosting station at Panchsheel Marg-Sardar Patel Marg Crossing for a capacity of 15 lac ltrs. wherein the water will be drawn from Palam Reservoir of DJB and further boosted.  An existing taxi stand and tubewell at this site will be got shifted to facilitate construction  of underground tank.

4.	Detailed Proposal of the Subject :

Installation of an online boosting pump by NDMC which feeds  entire Chanakya Puri Area including I.B. Complex, all Embassies  and Govt. Guests Houses  has been objected to by DJB and as such, it has been decided  that an underground reservoir of 15 lac ltrs. capacity be constructed at the Crossing of Panchsheel Marg-Sardar Patel Road.  This A/A and E/S estimate amounting to Rs. 2,80,32,900/- has been framed on plinth area rates for construction of  an underground reservoir of 15 lac ltrs. capacity at the Crossing of Panchsheel Marg-Sardar Patel Road wherein the water from Palam Reservoir will be drawn through feeder main and further boosted in Chanakya Puri Area. The estimate comprises of the following sub heads :-

i)	Construction of U/G tank 	 	-	Rs. 1,80,97,500/-

ii)	Construction of Pump House		-	Rs.   13,96,462/-

iii)	P/L Feeder & delivery  lines		-	Rs.    45,41,064/-

& shifting of existing lines.

iv)	Shifting of existing taxi stand (LS)	-	Rs.   2,00,000/-

v)	Shifting of tubewells (LS)		-	Rs.   2,00,000/-

vi)	Installation of pump set 	 	-	Rs.  27,81,287/-

& connections including electric

external connections.

Contingencies 3%			-	Rs,    8,16,489/-

5.	Final Implications of the Proposed Subject :

The Preliminary Estimate amounting to Rs. 2,80,32,900/- has been framed for obtaining administrative approval and expenditure sanction of the Council.   A provision of Rs. 5 lacs has been proposed in the revised budget proposals for the year 2007-08 and for Rs. 80 lacs  in the budget proposal for the year 2008-09.

6.	Implementation Schedule with Timeliness for each stage including Internal Processing :

After accord of administrative approval and expenditure sanction from the Council, the following time schedule will be implemented :-

a)	Approval of detailed estimate 		-	1  Month

after receipt of  structural drawings

b)	Approval of Draft NIT 			-	15 days

c)	Call of Tender 				-	1  Month

d)	Award of Work 				-	2  Months

e)	Execution of Work 			-           6 Months

7.	Comments of the Finance Department on the Subject :

The observations of the Finance Department dt. 22.11.07 were clarified and finally, Finance has observed as under :-

“We have no objection to the P.E amounting to Rs. 2,80,32,900/- (Rs. Two crore eighty lakh thirty two thousand nine hundred) for the work “Construction of Water Boosting Station at Panchsheel Marg-Sardar Patel Marg Crossing” subject to incurring no liability w/o ensuring hassle free shifting of taxi stand coming in the alignment of proposed scheme and removal of trees in accordance with the rules of Forest and Environment Deptt.

This issues with the approval of F.A.”

8.	Comments of the Department on Comments of Finance Department :

As regards shifting of taxi stand coming in the alignment of proposed scheme, the matter will be taken up with Director (Estate), NDMC with regard to this.  Regarding removal of trees, matter will be taken up with Forest and Environment Department separately.

9.	Legal Implication of the Subject :

Not applicable

10.	Details of Previous Council Resolutions, Existing Law of Parliament and Assembly on the Subject :

Not applicable

11.	Comments of the Law Department on the Subject :

Not applicable

12.	Comments of the Department on the Comments of Law Department :

Not applicable

13.	Recommendations :

The case is placed before the Council for consideration and accord of administrative approval and expenditure sanction to the preliminary estimate amounting to Rs. 2,80,32,900/- (Rs. Two crore eighty lakh thirty two thousand nine hundred only) for the above said scheme.

COUNCIL’S DECISION