ITEM NO. 18 (A-46)

1.	Name of the Project

Name of Work:- Up-gradation of Palika Bazar.

Sub Head: Up gradation/ Redevelopment of Palika Bazar.

2.         Name of the Department Concerned

Civil Engineering Department, EE(BM-III)

3.	Brief History of the Project

i)	Palika Bazar is one of the NDMC’s prestigious under ground market.  It is the only centrally air conditioned of NDMC with a green top.  It was developed in seventies and shops have been allotted on license basis.  These are on rehabilitation & on tender basis and present annual license fee collection from shop keepers is about Rs.5.21 crore.

Ii)	The NDMC has taken up up-gradation of its markets and buildings and sufficient amount has been provided in the NDMC Budget as a reserve fund for such up-gradation.

iii)	The Council, in its meeting dated 31/3/2008 had conceptually approved an estimate of Rs.11.00 crore for the up-grading of services in Palika Bazar.  This included Rs.2.00 crore for Civil works & Consultants fee. (Copy of agenda is enclosed as an Annexure “A” (See pages 166 - 168).

4.	Detailed Proposal of the Project & Scope of Work:

The proposal is for up-gradation/ renovation of Palika Bazar which will improve its acceptance by Public at large and customer visiting the market.  A detailed project report (DPR) was prepared for “Up-gradation of Palika Bazar” where in sub committee officers are from Civil, Electric, Architect and Fire Fighting departments. Comments from Estate department were also obtained for this project. Main items of work considered in the Preliminary Estimate are as given below:

- Dismantling old flooring, plaster, false ceiling etc.

- Flooring & Cladding- Marble, Ceramic Glazed tiles, Glass Mosaic Tiles, Vitrified tiles, Tac Tiles, etc.

- Stainless steel benches.

- Stainless Steel Hand rails.

- ACP work.

- Flex sheet sign borads.

- Improvement works of toilet with sanitary fittings.

- False Ceiling, etc.

5.	Financial Implications of the Project

Financial implication of the project is  Rs. 2,06,63,600/-.

6.	Implementation schedule with time lines for each stage including internal processing.

a)	A/A & E/S by the Council		-			August 2008

b)	Technical Sanction of Detailed Estimate	-			15/10/2008

c)	Approval of NIT				-			30/11/2008

d)	Call of Tenders				-			31/12/2008

e)	Award of Work				-			01/03/2009

f)	Completion of Work (12 months)	-			28/02/2009

7.	Comments of FA/ Finance Department dated    (Diary No. 342 dated. 14/08/2008)

In view of the position brought on record by the department, we have no objection if proposal/ estimate amounting to Rs. 2,06,63,600/- is placed before the Council in respect of the scheme already having conceptual approval of the Council, subject to the following condition:

- The department may bring the justification of items where the approved NDMC norms/ specifications for commercial buildings have been deviated

- Availability of funds for execution of work.

- FD is of the view that license fee can be considered to increase in terms of provisions of FR-45B and also having regard to the policy, if any approved by the Council on the point at issue in respect of all the commercial complexes where improvement works are being carried out,.

- Comments of the Department on the comments of FA/ Finance Department

- It is submitted that Preliminary Estimate is based on the circular issued by ENC for specifications for Commercial Complexes for most of the items. However, other items have been taken as mentioned in the Architectural/ Redevelopment drawing for Palika Bazar duly approved/ issued by Chief Architect, NDMC to make Palika Bazar a commercial market of international standard.

- Sufficient funds are available in the current year budget book. More funds shall be requested in revised budget in due course.

- Revision of license fee as pointed out by FD as per FR-45B is placed before the Council for consideration.

9. 	Legal Implication of the subject/ project

Nil

10.	Details of previous Council Resolutions, existing law of Parliament  and assembly  on the subject.

Scheme has been duly approved by the Council in its meeting held on 31.3.2008 vide item no. 06(A 83)

11.	Comments of LA/ Law Department

Nil

12.	Comments of the Department on the comments of LA/ Law Department

Nil

13.	Certified that all Central Vigilance Commission (CVC) guidelines have been followed while processing the case.

14.	Recommendations :.

Preliminary Estimate amounting to Rs. 2,06,63,600/- for “Up-gradation of Palika Bazar for the Sub Head: Up gradation/ Redevelopment of Palika Bazar”  duly concurred in by the finance department  is recommended for A/A & E/S of the Council.

COUNCIL’S DECISION

Resolved by the Council to accord administrative approval and expenditure sanction to the preliminary estimate amounting to Rs.2,06,63,600/- for upgradation of Palika Bazar for the SH : Upgradation / Redevelopment of Palika Bazar.