ITEM NO. 4 (A-50)

1.	Name of  the Sub. 	:Strengthening of Water Supply System in NDMC

Area.

Sub Head     :Const. Of  U.G.Tank with boosting arrangement at

Kali Bari Marg near Water Supply Control Room.

- Name of the Deptt.	:Civil Engineering, Public Health Circle, Water Supply

Division.

- Brief History of the Subject

The supply of water to NDMC area from Talkatora Reservoir is through gravity flow.  As the Reservoir does not have requisite water levels and duration of water supply is less,  as such, the pressure in the line is also very low &  complaints of low water pressure are received from DIZ Area, RML Hospital, MP’s/Minister’s Bungalow Area, President Estate and adjoining areas.  Consequent upon this, necessity of water boosting station i.e. construction of underground tank with boosting arrangement  has been felt during discussions held at various levels including meetings held with various RWA’s under the chairmanship of Hon’ble Chief Minister, Delhi.   Necessary field survey has been carried out and it is found that construction of underground tank with boosting arrangements is feasible in the vacant plot measuring about 3000 sq.m. in area     at Kali  Bari Marg near Water Supply Control Room.  As per size of the plot, it is feasible to construct an underground tank of  approximately  30.00 lac ltr capacity with a pump house which will house 5 No. electric pumps & motors of 100 Horse power capacity.  Feeder line to this underground tank will be provided from the 27” dia line coming from Talkatora Reservoir and water will be boosted in the existing network to increase the pressure.

The plot for construction of underground tank is owned by L&DO and for  allotment of this plot to NDMC, a separate request has been made to L&DO. This is also included in combined land allotment case as  taken up  by the Office of S.O. to Chairman.

- Detailed Proposal of the Subject :

As per standing order No. 15 dt. 7.6.05,   a  Sub Committee comprising of SE(PH), SE(BM-II), EE(P-III), EE(W/S) and AE(W/S)  to prepare the Project Report has been nominated by Chairperson for SE(PH) Circle, circulated vide No. D-48/SE(PH) dt. 17.04.07.  The nominated Sub Committee have considered the scheme and is of the opinion that an underground tank with approximate capacity of 30.00 lac ltrs. With boosting arrangements should be constructed at Kali Bari Marg to store water received from Talkatora Reservoir and further boost the same in the existing network to increase the pressure.

It has, therefore, been proposed to construct an underground R.C.C. tank with the approximate capacity of 30.00 lac ltrs. With the provision  of a pump house, pump sets and connections, feeder and delivery line and boundary wall etc.

- Final Implications of the Proposed Subject :

The Preliminary Estimate amounting to Rs. 5,21,00,000/- has been framed and duly scrutinized by SSW’s  Office.  There is no budget provision for this scheme in the current year’s budget, however, a provision of Rs. 2.00 lacs have been sought in R.E. and Rs. 50.00 lacs in B.E. for the year 2008-09.

6.	Implementation Schedule with Timeliness for each stage including Internal Processing :

After approval of Preliminary Estimate and accord of the administrative approval and expenditure sanction from Council and allotment of land from L&DO, the following time schedule will be implemented :-

a)	Approval of detailed estimate 		-	3  Months

after receipt structural drawings

b)	Approval of Draft NIT 			-	1  Month

c)	Call of Tender 				-	1  Month

d)	Award of Work 				-	3  Months

e)	Execution of Work 			-        12  Months

- Comments of the Finance Department on the Subject :

The observations of the Finance Department dt. 09.10.07, 22.10.07 were clarified and finally, Finance has observed as under :-

“We concur in the PE amounting to Rs. 5.21 crores (Rupees Five Crore Twenty One Lakh) for the work “Strengthening of Water Supply System in NDMC Area – Construction of U/G Tank with boosting arrangement in Kali Bari Marg near Water Supply Control Room being a fast track scheme as checked by  Planning subject to that there is no other alternate solution with lesser financial involvement to cope with the existing water problem of DIZ area and it will serve the intended purpose of the scheme.  In addition, abstract of cost may be got signed from CEI for authentication.  The department is advised to seek assistance for W/S Scheme under JNNURM for which requisite DPR in terms of vision document (CDP), on priority, be processed.

This issues with the approval of F.A.”

- Comments of the Department on Comments of Finance Department :

As observed by Finance Department, CEI has signed the abstract of cost.  As regards, seeking assistance for Water Supply Schemes under JNNURM, this scheme is presently not covered under the same.

- Legal Implication of the Subject :

Not applicable

- Details of Previous Council Resolutions, Existing Law of Parliament and Assembly on the Subject :

Not applicable

- Comments of the Law Department on the Subject :

Not applicable

- Comments of the Department on the Comments of Law Department :

Not applicable

- Recommendations :

The case is placed before the Council for consideration and accord of administrative approval and expenditure sanction to the preliminary estimate amounting to Rs. 5,21,00,000/-  (Rupees Five Crore Twenty One Lakh only) for the above said scheme subject to allotment of land by L&DO.

COUNCIL’S DECISION

Resolved by the Council that administrative approval and expenditure sanction to the preliminary estimate amounting to Rs.5,21,00,000/- is accorded for the said scheme for ‘Strengthening of Water Supply System in NDMC area’.