ITEM NO. 08 (A-03)

- Name of Project: - Rehabilitation of old sewer.

Sub-Head. 	Desilting and rehabilitation of 1100 mm & 1200 mm dia sewer line at Ashoka Road from Nirvachan Sadan to C Hexagon.

(Preliminary Estimate Thereof).

- Name of the Department concerned :  Civil Engineering, Public Health Circle, Sewer Project Division.

- Brief History of the Project:

The Preliminary estimate amounting to Rs 7,87,53,000/-  has been framed to cover the cost of desilting and rehabilitation of the existing sewer line from Nirvachan Sadan to C-Hexagon at Ashoka Road. The existing sewer line was laid in 1977 by laying NP2 class RCC pipe from Bhai Veer Singh Marg via Gole Dakkhanna Nirwachan Sadan to C-Hexagon being it outfall into 84 inch dia brick barrel running along C-Hexagon and out lived its life. The up stream portion of this sewer line from Bhaiveer Singh Marg to Gole Dakkhanna to Nirwachan Sadan has been recently rehabilitated by CIPP technology. This proposal is for rest of downstream portion of this remaining sewer line.  Due to formation of cavities the sewer line was collapse during Mansoon season on August 16, 2010 at roundabout of Ashoka Road and Man Singh Road near Andhra Bhawan. This created an emergency situation and temporary arrangements were made to make through the road. To avoid any future emergency a permanent solution of the problem is being sought by rehabilitation the old and out lived sewer line by CIPP technology. Therefore, the rehabilitation of the line is proposed to be taken up with CIPP technology after recommendation of consultant IIT Delhi who was appointed to study the sewerage network in NDMC area. A technical subcommittee was formed to evaluate the existing condition of existing sewer line, finally the subcommittee was of the view that this sewer line may be rehabilitated from NIrwacha sadan to C-Hexagon at Ashoka Road.

The propose sewer line 1864 m running from Nirwachan Sadan to C-Hexagon at Ashoka Road and the sewage flowing thorough this sewer line further discharge into  trunk sewer of dia 2200 mm dia for its final disposal.

- Detailed Proposal on the project:

The proposal contained for the rehabilitation in a length of 1864 metres of dia 1100 & 1200 mm sewer line including desilting. The technology to be used shall be CIPP liner which is considered most suitable and recommended by IIT Delhi.

- Financial Implications of the proposed project :

There exists a budget provision of 2.00 lakhs under RE for year 2011-12 and  Rs 75 lakhs under BE for year 2012-13 under head  52.412.40.4.20.1.116 at page no. 359 of budget book 2012-13 Vol.2. The total length proposed for desilting and rehabilitation 1864 m

- Implementation Schedule with Timeliness for each stage including Internal Processing:

After approval, the implementation schedule will be as under:-

Technical sanction/DE 						06 weeks.

Preparation and approval of draft NIT				06 weeks.

Call of tenders 							08 weeks

Award of work 							04 months.

The execution of works						12 months.

- Comments of the Finance Department on the Project:

The Finance department has concurred  the proposal of the department vide Dy. No 2136 dt 15.11.2011 and further vide diary no. 95 dt. 12.01.2012 the finance dept. advised to process the case by  updating the budget provision as per RE 2011-12 and also mentioning the length of proposed for desilting and rehabilitation.

- Comments of the Department on Comments of Finance Department:

The department has added the DPR and brought on record the recommendations of technical subcommittee as per requirement of finance department.

The budget provision as per revised estimate 2011-12 has been modified in draft agendum at Serial no. -05  and the length of the proposed sewer line incorporated.

- Final views of Finance Department:

Finance department concurred the proposal vide diary no 671 dt. 15.03.2012.

- Legal Implication of the Project:

--Nil--

- Details of previous Council Resolutions. Existing Law of Parliament and Assembly on the subject:

--Nil—

- Comments of the Law Department on the subject / project:

It has no legal issue.

- Comments of Department on comments of Law Department:

--Nil—

- Final view of Law Department: ( Whenever necessary)

--Nil--

- Certificate that all Central Vigilance Commission’s (CVC) guidelines have been followed while processing the case.

It is certified that all the CVC guidelines have been followed.

- Recommendations:

The case is laid before the council for the consideration and accord of A/A&E/S for an amount of Rs.7,87,53,000/- for the work of “Rehabilitation of old sewer. SH:-Desilting and rehabilitation of 1100 mm & 1200 mm dia sewer line at Ashoka Road from Nirvachan Sadan to C Hexagon.”

COUNCIL’S DECISION

Resolved by the Council to accord administrative approval and expenditure sanction to the estimate amounting to `.7,87,53,000/- for the work of “Rehabilitation of old sewer - Desilting and rehabilitation of 1100 mm & 1200 mm dia sewer line at Ashoka Road from Nirvachan Sadan to C Hexagon.”