ITEM NO. 35 (A-102)

1. 	Name of the subject/project

Sub: S/R of Roads in NDMC Area.  SH: Provision of Common Utility Duct at S.P. Marg

2. 	Name of the Department

Civil Engineering Department, C.P. Project Division

3. 	Brief history of the subject/project

- The frequent faults occurring in underground services especially in electrical & communication cables results in digging/ cutting of the footpath/ developed area/ paved area in the Right of the Way of Roads.  The digging/ cuttings are also caused due to laying of fresh electrical and communication cables for augmentation/ replacement of old/ damaged cables.

- The cuttings at regular intervals throughout the year and restoration work done thereafter by road cutting agencies gives unpleasant look along the road side.  In fact restoration to original specifications/ designs especially in footpath can never be achieved due to mismatch between old & new material.

- To avoid these problems of frequent cutting of footpaths and paved/green areas in Right of Way of roads underground corridor is constructed called Common Utility Duct or Duct Bank to lay the communication cables, electrical cables, road lighting cables, water supply & gas lines etc.  The existing services i.e. LT/HT cables, water supply lines etc. cannot be shifted due to huge costs involved but future cables can be placed in these Common Utility Ducts by way of replacement/ augmentation/ alteration.  The drainage & sewerage lines being gravity flow laid at more depth are generally laid outside of these duct banks.

- Provision of Common Utility Duct or duct bank is made of HDPE/ PVC pipes encased all around by concrete & laid either in green/ paved area of Right of way or below the footpath with accessible manholes.  These duct banks are required to be provided along the roads on both sides with the cross ducts below the carriageway at certain intervals to have full connectivity along and across the roads.

- The advantages of Common Utility Duct are Reduction of maintenance manholes, one time relocation and less excavation and repairs, allows rapid access to all utilities without having to dig access trenches due to confused and often inaccurate utility maps, keeps roads smoother, public safety, increases the quality of life and reduces social cost.

- The Empowered Committee during its meeting on 27 Aug.’08 &  08 Oct.’08 decided that ducting for laying of services be provided on S.P. Marg & Mother Teresa Crescent to begin with to avoid damage to road/footpath on account of frequent cuttings by various service providers & remaining roads be taken up in a phased manner.  It was decided that Core Group comprising CE(C)-I, CE(E)-II, ACE(C) & Director (Hort.) be formed to work out modalities of project including arriving at a design capacity etc. after consultations with various stakeholders like Electrical Engineering Department, Telecom Service Providers, IGL, Public Health & Horticulture Department. It was also decided that suitable bylaws under NDMC Act be framed for levy of fixed/ service charges from service providers for capital/ maintenance cost of duct banks in consultation with Law Department.

- So proposal was made to provide Common Utility Ducts/ Duct Bank on S.P. Marg.  Accordingly, consultations were held with Telecom Providers, IGL, Water Supply Department and the requirements to design the Common Utility Duct have been given by these departments.

- The design of Common Utility Duct has been prepared in-house based on the inputs received from service providers, Electrical Department & based on the recommendations of Core Group comprising of CE(C)-I, Director (Hort.), CE(E)-II & ACE(C).

- Depending upon site conditions these common utility ducts are proposed below green areas, walkways, cycle tracks/service roads along all major roads in NDMC Area.

- The detailed presentation on Common Utility Duct was made to Hon’ble Lt. Governor at Raj Niwas on 10 Jun.’09 where members of UTTIPEC were also present.  After appreciating the efforts put in by NDMC for this novel concept Hon’ble Lt. Governor directed that other road owning agencies should also take up the case for provision of Common Utility Duct along the roads in the right earnest in view of its inherent advantages.  The copies of minutes dated 06 Aug.’09 & 16 Sep.’09 are enclosed as Annexure ‘A’ & ‘B’ (See pages 306 – 327)

- The Preliminary Estimate for provision of Duct Bank for S.P. Marg for Rs. 19,14,85,000/- was approved by the Council vide Agenda Item No. 04(A-64) dated 21 Aug.’09.

- Accordingly tenders were opened through e-tendering system.  The technical bid was opened on 10 Sep. ’09 and financial bid on 15 Sep.’09.  The details of eligible tenders received are as follows:-

| S. No | Name | Estimated Cost | Tendered Amount | Rate Quoted | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1. | M/s M.V. Omni Projects India Ltd. | Rs.18,62,91,555/- | Rs.19,88,60,269/- | 6.75% above | Lowest |
| 2. | M/s Tirupati Cement Products | -do- | Rs.24,06,62,502/- | 29.19% above |  |

- M/s M.V. Omni Project India Ltd. was the lowest bidder @ 6.75% above the Estimated Cost of Rs. 18,62,91,555/- against the justification 9.98% above the Estimated Cost with the tendered amount of Rs.19,88,60,269/-.  Since the rates quoted by bidder in similar work on Mother Teresa Crescent were lower so negotiations were conducted with lowest bidder after approval by the Competent Authority.  After negotiation the negotiated offer works out to 4.61%  above the Estimated Cost of Rs. 18,62,91,555/- against the justification of 9.98% above the Estimated Cost with the negotiated tendered amount of Rs.19,48,83,064/-.

- The rates quoted by the lowest bidder after scrutiny by Planning have been found to be reasonable and recommended for acceptance by the Council.

- The Finance Department has concurred the proposal.

- The validity of tender is upto 08 Dec.’09.

4. 	Detailed Proposal on the subject/ project

- Electrical Duct Bank

- A dedicated Concrete Encased Duct Bank comprising of HDPE pipes encased in concrete for Electrical cables for road lighting, traffic lighting, 11 KV, 33 KV, 66 KV & 220 KV on both sides of road.

- Communication Duct Bank

The dedicated duct bank of HDPE pipes encased in concrete for Communication cables on both sides & across the road.

  - Gas Duct

A separate soft corridor for Gas line has been planned towards Hotel side where pipes would be laid by the IGL.  No Gas corridor is required on Ridge Side as confirmed by IGL.

  - Water Supply & Irrigation Line Duct

    - A Separate soft corridor has been earmarked for laying of irrigation line under Streetscaping Project & two water supply lines on Hotel side & one on ridge side in future.

  - Drainage & sewerage lines would be outside the proposed duct bank.

5. 	Financial implications of the proposed project/subject

The financial implications of the proposal works out to Rs.19,48,83,064/-.

6. 	Implementation schedule with timeliness for each stage including internal processing

The schedule time for completion of project is Seven months after award of work.

7. 	Comments of the finance department on the subject

The Finance Deptt. vide diary No.2241 dated 24/25 Sep.’09 has concurred the proposal of award of work to lowest bidder.

8. 	Comments of the department on comments of Finance Department

No comments in view of concurrence of Finance Department.

9. 	Legal Implications of the subject/project

Nil

10. 	Details of previous council Resolution existing law of Parliament and Assembly on the subject

Administrative Approval and Expenditure Sanction for Rs.19,14,85,000/- was accorded by Council vide Agenda Item No. 4(A-64) dated 21 Aug.’09.

11. 	Comments of Law Department on the subject

No comments.  
 
 12. 	Comments of the department on the comments of the Law Department

No comments.

13. 	Certification by the department that all central vigilance commission (CVC) guidelines have been followed while processing the case

Certified that all necessary CVC guidelines have been followed during tendering.

14. 	Recommendations

The case is placed before the Council for consideration and accord of approval of following:

      - To award the work to M/s. Omni Project India Ltd. at their negotiated tender amount of Rs.19,48,83,064/- which is 4.61% above the estimated cost of Rs.18,62,91,555/- against the justification of 9.98% above the estimated cost of Rs.18,62,91,555/- for “Provision of Common Utility Duct at S.P. Marg”.

      - To initiate further action in anticipation of confirmation of Minutes of the Council meeting.

COUNCIL’S DECISION

Deferred.

It was resolved by the Council to cancel the tenders and to take up the work after the Commonwealth Games, 2010.