ITEM NO. 20 (A-61)

- Name of Subject :-

Construction of staff quarters for service personnel Sector-VII , Pushp Vihar , New Delhi.

- Name of the  Department:-

Civil Engineering Department Zone-II

- Brief History of the Subject :-

Construction of building and maintenance of dwelling houses for Municipal Officers and other employees is one of the discretionary function of the Council under section 12(n) of NDMC Act 1994. Accordingly L&DO was requested to make available land for construction of staff quarters for service personnel.   
          A piece of land measuring 1.98Acres was allotted to NDMC by L&DO vide letterL&DO/LV/16/(716)/490 dt. 28.08.2001 but  physical  possession of only 1.609 Acres of land was handed over to NDMC on  27-12-01 Cost of land has since  been deposited  with  L&DO for Rs 19,800/-

After getting physical possession the boundary wall was constructed around the plot. The security guard was also made depute security to avoid any encroachment.

Architect department issued drawings for housing of service personnel  comprising 96 Type-II Quarters along with  E/S/S &  pump house  in Four storied blocks.

Based on  architectural drawing , Preliminary  estimate based on  PAR 1992 was prepared for Rs.6,73,46,000/- and  approved  by council  vide  Reso. No. (A-14) dt. 28.9.05.

The lay out plan was received duly approved by MCD on 12.09.08, though the same was submitted to them for approval on 04.10.05 Subsequently plan was submitted to DUAC and CFO Delhi for clearance. DUAC raised certain  observations regarding  stilt  parking . Accordingly modified plan and  model has been   submitted  to DUAC for approval. DUAC have approved the plans  with  observation i.e. a proper landscape plan with input of qualified landscape architect needs to be submitted. Accordingly Architect deptt. have  submitted the  landscape plan.  The plan was cleared by CFO and DUAC on 28.01.09 and 03.06.09

As  a result of  change in plan  as per  observation of  DUAC  and the fact that  earlier  estimate approved  was  based on PAR 1992  there was a  requirement   to revise  the estimate  and seek revised admistrative  approval.

Details  of  major items in respect of previous sanction  &  proposed  revise sanction are as under  :-

| Sl No. | Description of item | Amount in Revised Original P.E. P.A.R. 1992 | Amount in revised P.E. PAR. 2007 |
| --- | --- | --- | --- |
| 1 | Housing civil work | 4,93,68,424/- | 8,88,90,832/- |
| 2 | ESS, U/G Sump and Pump House | 1,21,60,790/- | 1,74,64,980/- |
| 3 | Development | 38,55,703/- | 1,06,42,593/- |
|  |  | 6,53,84,917/- | 11,69,98,405/- |
|  | 3% contingencies | 19,61,548/- | 35,09,952/- |

Rs.6,73,46,465	     12,05,08,357/-

Say Rs.6,73,46,000/-          Rs.12,05,09,000/-

- Detailed  proposal  of the  subject :-

Considering   the observations of  DUAC  a modified plan  was made and released by Architect deptt. The modified plan comprises 96 Type-II quarter for 4 storied along with stilt parking in12 blocks of eight quarters each are to  be constructed .

Specification on the basis of  PAR 2007 has been  adopted  in the  Revised  Preliminary Estimate  as per details given below:-

Flooring

Mosaic Flooring            In  all Rooms, Kitchen, WC &  Bathrooms.

Kota stones flooring      In common  circulation  area &  staircases.

Ceramic glazed tiles on wall in WC, Bathroom  &

Kitchen.

Door & Window

Frame work                   For Windows  pressed steel frame,

For Doors Tee Iron frame.

Shutter                           35 mm thick panelled shutter,

Solid PVC shutter 20mm thick for WC & bath .

Finishing

Inside                          POP  plaster finished  with oil bound  distemper in rooms,

White wash on Kitchen, Bath, WC & ceiling

Outside                       Washed stone grit  plaster

Terrace finish             Mud  phaska

Over head                   500 litrs water tank for each  flats

- Financial  implication  of the proposed  Project / Subject :-

On the basis  of  modified architectural  drawings , revised preliminary  estimate amounting  to Rs.12,05,09,000/- has been prepared based on PAR 2007 , DSR 2007 with  cost  index, duly checked by planning  division was  forwarded  to Finance  and have concurred the same for Rs.12,05,09,000/-

- Implementation schedule with time lines for each stage including internal processing :-

Time of completion of the project 2 years after the award of work.

- Comments of the Finance department at the subject:-

  - Ensuring & certifying that the project in question involves landscape related construction and

  - While submitting the proposal to Chairman for approval of the Council. Clear recommendation duly signed by HOD be recorded, in compliance of contents of Circular No. EIC/D/PS/301 dated 23.02.2005 issued by the then E-in-C.

- Comments of the department on the comments at the Finance department:-

  - It is certified that after Construction Land Scapping is also required.

  - Recommendation have been recorded.

Finance Department have seen and they have no further comments.

- Legal Implication of the Subject / Project.

NIL

- Details  previous council resolution/ existing and of Parliament and assembly on the Subject.

Previous council Reso No. 2(A-14) dt. 28.09.2005.

- Comments of the Law department on the subject / Project.

The Estimated Cost on 2005 was Rs.6,73,46,000/-. It is now Rs.12,05,09,000/- delay & reason for increasing Cost may be explained in the proposal.

- Comments of the department on the comments of Law department.

The lay out plan was received duly approved by MCD on 12.09.08, though the same was submitted to them for approval on 04.10.05 Subsequently plan was submitted to DUAC and CFO Delhi for clearance. DUAC raised certain observations regarding stilt  parking. Accordingly modified plan and model has been submitted to DUAC for approval. DUAC have approved the plans  with observation i.e. a proper landscape plan with input of qualified landscape architect needs to be submitted. Accordingly Architect deptt. have  submitted the  landscape plan.  The plan was cleared by CFO and DUAC on 28.01.09 and 03.06.09.

- Certification by the department that all central Vigilance Commission (CVC) guidelines have been followed, while processing the case.

Certified that necessary   guidelines of CVC have been   followed , while processing  the case.

- Recommendation

The  case is placed before the council  for  according  Revised Preliminary     Estimate amounting  to Rs.12,05,09,000/-for  the construction  of staff quarters. It is also  resolved that  further  action in  the matter be  taken in anticipation  of confirmation of the  minutes by the  council .

- Draft  resolution:-

Resolved by  the council that revised  A/A & E/S is accorded to the   preliminary estimate amounting  Rs.12,05,09,000/- for  construction of  staff  quarters  for service  personnel  at     Sector -7 Pushp Vihar, Saket .

It was also  resolved  that  further  action  in the  matter  be taken  in anticipation   of confirmation  of minute’s by  the council .

COUNCIL’S DECISION

Resolved by  the Council to accord revised administrative approval and expenditure sanction to the   preliminary estimate amounting  Rs.12,05,09,000/- for construction of  staff  quarters for NDMC employees at Sector -7 Pushp Vihar, Saket .

It was also resolved that further action in the matter be taken in anticipation of confirmation of the minutes by the Council.