Item No. 3 (A-42)

1.	Name of the subject/project		:	S/R of roads in NDMC area during 							2006-07.

Sub-Head				:	Providing and laying Mastic 					asphaltic wearing course at Kaka 				Nagar Colony service roads.

2.	Name of Department			:	Civil Engineering Department

Road-I division.

3.	Brief history of the subject/project	: The conditions of the service roads of Kaka Nagar colony has deteriorated due to lapse of time.  Number of cracks, pot holes have developed over the entire surface of carriage way, disintegration of road surface have also started at places.  The Kaka Nagar colony was inspected by Smt. Tajdar Babar, MLA, Govt. of NCT Delhi & Vice Chairperson, NDMC alongwith representative of Residence Welfare Association of Kaka Nagar and Bapa Nagar and NDMC officials on 12.12.05 and it was desired to resurface roads of Kaka Nagar colony.  Again the area was inspected by Area MLA & Vice Chairperson, NDMC with E-in-C, SE(R)Z-I and other NDMC officials on 05.10.06 and it was emphasized the necessity of mastic asphaltic wearing course.  Keeping in view of the performance assessed in the adjoining Sundar Nagar colony under the jurisdiction MCD, where mastic treatment work was done. E-in-C has approved the proposal for providing mastic asphalt treatment for Kaka Nagar colony.  The Preliminary Estimate amounting to Rs. 96,08,000/- has been concurred by finance department after scrutiny in planning.

4.	Detailed proposal on the subject/project:-	25 mm thick bitumen mastic asphaltic course shall be provided in the entire service roads of Kaka Nagar in an area of approx 21500 square metre after applying tack coat with paving bitumen 80/100 @0.5 Kg/square metre.  Provision for filling depression has been taken wherever, the surface is totally worn out.

5.	Financial implication of the proposed project / Subject:- 	The Preliminary estimate for the work is for Rs. 96,08,000/-.  The necessary funds are available to meet the expenditure against the budget provision of Rs. 1500 lacs vide item No. 239 page 110 under the head of G.1.3 S/R of roads in NDMC area.  Funds for this project has been sought in the revise allocation of the funds for the financial year 2007-08.

6.	Implementation schedule with timelines for each stage including internal preocessing:-

The following schedule has been prepared for implementation:-

a)	Sanction of Preliminary Estimate 				31.01.07

b)	Sanction of Detailed estimate					15.02.07

c)	Sanction of NIT and issuance of press notice			15.03.07

d)	Call and opening of tenders 					30.04.07

e)	Award of work							15.07.07

f)	Completion of work						25.11.07

7.	Comments of the finance department:- The Finance has concurred the proposal subject to the following :-

- Adequacy of the funds

- Setting right all services including drainage system

- Fixation of life of surface done with mastic treatment in terms of letter of CRRI dated 23.11.2003.

- Execution of work in Kaka Nagar Colony on experimental basis through mastic treatment.

8.	comments of the Department on comments of finance department:-	The clarification of the points raised by finance department are as under:-

- Sufficient funds are available.

- The services like water supply, sewerage, drainage etc are being provided on the katcha of Kaka Nagar as such main carriage way will not be disturbed for cutting etc.

- The defect liability period for mastic treatment in Colony Road is considered as five years and the life span is seven years.

- It has been proposed to execute mastic treatment work on the experimental basis in Kaka Nagar colony only.

9.	Legal implication of the subject/project:-		Nil

10.	Details of previous council Reso. existing law of parliament and Assembly on the subject:-	 					Nil

11.	comments of Law Department on the subject:-	No comments.

12.	Comments of the Department on the comments

of the Law Department:-				Not applicable.

13.	Recommendations:-	The case is laid before the council for according administrative approval & expenditure sanction amounting to Rs. 96,08,000/- for the work of Providing and laying Mastic asphaltic wearing course at Kaka Nagar Colony service roads.

COUNCIL DECISION

Resolved by the Council that administrative approval and expenditure sanction amounting to Rs.96,08,000/- is accorded for the work of providing and laying Mastic asphaltic wearing course at Kaka Nagar Colony service roads.