ITEM NO.07 (A-19)

- Name of the Subject/Project.

Strengthening and resurfacing of roads in NDMC area

during 2005-2006 by Hot Mix Technology. Revised Estimate thereof.

- Name of Department

Civil Engineering Department

- Brief History of the Subject/Project

52 roads were identified for the resurfacing with the recommendations of two consultants that were appointed for this purpose viz. Noida Toll Bridge Company Ltd. (NTBCL) and Central Road Research Institute (CRRI) and finally it was decided to carry out resurfacing of roads by Hot Mix Technology and Micro surfacing.

The following roads are being resurfaced by using Hot Mix Technology:

- AFRICA AVENUE

- ASHOKA ROAD

- ARCHBISHOP MAKARIOS MARG

- BANGLA SAHIB MARG

- DR. S. RADHA KRISHNAN MARG

- DR. ZAKIR HUSSAIN MARG

- FEROZE SHAH ROAD

- K. G. MARG

- MADHU LIMAYE MARG

- MOTHER TERESA MARG

- SAFDAR HASHMI MARG

- SATYA MARG

- TANSEN MARG

- TEEN MURTI MARG

- TOLSTOY MARG

- UDYAN MARG

- VINAY MARG

- SOUTH END ROAD

- SHANTI PATH

- JANTAR MANTAR ROAD

- MADHAV RAO SCINDHIA MARG

- PANDARA ROAD

- RAJPATH

- HANUMAN ROAD

- SANSAD MARG

- AUROBINDO MARG

- JOR BAGH ROAD

- SAFDARJUNG ROAD

- MAULANA AZAD ROAD

The administrative approval & expenditure sanction amounting to Rs. 1899.42 lacs was accorded by the Council vide Resolution No 5(A-6), dated 17.05.2006.

The tender was awarded to the M/s Satya Prakash & Bros. Pvt. Ltd. at their quoted rate of 39.97% above the estimated cost at a total tendered amount of Rs. 25,55,65,251/- vide Resolution No. 05 dated 19.07.06. Since, the tendered amount exceeds administrative approval, amount by more then 10% revised administrative approval is required.

- Detailed Proposal on the subject/project.

The scope of work and specifications adopted in the work are as under:

  - Tack coat @ 0.25 Kg per sqm with bitumen emulsion complying with IS:8887-19953

  - Filling depressions in the road surface using bitumen 60/70.

  - 40mm to 50 mm thick dense bituminous macadam (DBM) using 60/70 grade bitumen to achieve a density of 2.352 gm/cc with 4.9% bitumen, as leveling course for camber/profile correction.

  - 40-50 mm tick bituminous concrete (BC) as overlay, using PMB-40 grade bitumen to achieve a density of 2.360 gm/cc with 5.4% bitumen.

  - Sealing the cracks by using hot rubberized bitumen 80/100

  - Road marking with thermoplastic paint, applied mechanically.

- Financial implication of the proposed project/subject.

Details of estimated cost, lowest tender cost and justified cost are as under:-

| S. No. | Description | Amount in Rupees & % |
| --- | --- | --- |
|  | Tendered Cost (Lowest) | Rs. 25,55,65,251.00 (39.97% above the estimated cost put to tender of Rs. 18,25,91,290.00) |
|  | 15% for the drainage improvement on Rs. 25,55,65,251.00 | Rs. 3,83,34,788.00 |
|  | Total | Rs. 29,39,00,039.00 |
|  | Contingencies @ 3% on Rs. 29,39,00,039.00 | Rs. 88,17,001.00 |
|  | Departmental charges @ 8% on the estimate being charged to plan fund estimated cost Rs. 5,55,88,431.00 | Rs. 44,47,074.00 |
|  | Amount for third Party Quality Audit | Rs. 49,55,664.00 |
|  | Total | Rs. 31,21,19,778.00 |
|  | Say | Rs. 31,21,20,000.00 |

The necessary funds are available under Budget Provision of Rs. 1400.00 lacs vide item No. 46 Page 148, during the financial year 2007-08.

- Schedule with timeliness for each stage including internal proceedings.

The work has been awarded to M/s. Satya Parkash & Bros. Pvt. Ltd on 28.08.06 and is in progress.. First layer of DBM has been provided on 19 roads. Work on six roads has been completed

- Comments of the Finance Deptt on the subject.

Finance Deptt has concurred proposal for seeking revised administrative approval and expenditure sanction for an amount of Rs. 31,21,20,000/- (Rupees Thirty One Crore Twenty One Lakh Twenty Thousand only)

- Comments of the Department on comments of Finance Department.

No Comments

- Details of previous Council Reso. Existing law of parliament and assembly on the subject.

The administrative approval and expenditure sanction of this work was accorded for Rs. 1899.42 lacs by Council vide item no. 5 (A-6), dated 17.05.2006 and the work was awarded to M/s. Satya Parkash & Bros. Pvt. Ltd. for Rs. 25,55,65,251/- vide council resolution No. 05 dated 19.07.06

- Comments of Law Department on the Subject.

No legal issues are involved. The case has been concurred by Law deptt.

- Comments of the Department on the Comments of the Law Department.

Not applicable

- Recommendations

The case is placed before the Council to accord revised Administrative Approval & Expenditure section for Rs. 31,21,20,000/- (Rs. Thirty one Crores twenty one lacks twenty thousand only) for the work Strengthening and resurfacing of Road in NDMC area during 2005-06 Hot Mix Technology.

COUNCIL’S DECISION

Resolved by the Council that the revised administrative approval & expenditure sanction for Rs.31,21,20,000/- is accorded for the work of strengthening and resurfacing of Roads in NDMC area during 2005-06 by Hot Mix Technology.