Item No. 03 (A-48)

1.	Name of the Subject / Project :

Sub.:  Streetscaping of roads in NDMC Area

SH :   Streetscaping of Mother Teresa Crescent

2.	Name of the Department :

Civil Engineering Department, Road-IV Division

3.	Brief History of the subject / project :

(a)	A decision was taken in year 2006 to take up important roads for streetscaping and M/s Creators Architect & Interior Designers was appointed as a landscape consultant for streetscaping of Sardar Patel Marg and Mother Teresa Crescent.

(b)	Accordingly as per terms of agreement the consultant submitted the conceptual design for proposed streetscaping of Mother Teresa Crescent.

(c)	A presentation of conceptual design was made to Chairperson & Zonal Officers / HODs on 17 Jan.’06 when some suggestions were made.  Presentation of modified plan was made to E-in-C on 27 Apr.’06 & Chairperson, E-in-C & other officers on  09 Jun.’06.

(d)	The presentation of the conceptual plan was also made to Secretary to President of India on 01 Sep.’06.  Secretary to President of India was of the opinion that streetscaping elements like paving, planters, pillars, benches etc. be constructed in Right of Way of Mother Teresa Crescent in conformity with what is existing inside the presidential estate and the conceptual plan was generally approved by the Secretary to President of India.

(e)	The conceptual plan of Mother Teresa Crescent was finally approved by Competent Authority on 01 Dec.’06.

(f)	The presentation of the conceptual plan was also made to Council vide Agenda Item No. 09(A-51) dated 21 Nov.’07.

(g)	Based on the approval of conceptual plan M/s Creators Architect & Interior Designer has submitted details of measurement, analysis of rates alongwith Preliminary Estimate.

(h)	The Preliminary Estimate for Rs. 9,05,35,500/- prepared by the consultant has been checked by the Member Planning of the project team.

(i)	The Preliminary Estimate has also been concurred by Finance Department.

(j)	The streetscaping of Mother Teresa Crescent alongwith other roads has been put on fast track and a project team has been constituted for execution of work.   The Empowered Committee after detailed deliberations has approved the Preliminary Estimate for Streetscaping of Mother Teresa Crescent & recommended that Preliminary estimate be placed before the Council for accord of Administrative Approval & Expenditure Sanction for Rs. 9,05,35,500/-.

(k)	It has also been decided by Empowered Committee that ducting for laying of services be provided under Streetscaping Plan so as to avoid damage to roads/footpaths on account of frequent cuttings by various agencies like Electrical & Telecommunication etc.  The Preliminary Estimate for ducting would be placed before the Council separately for accord of Administrative Approval & Expenditure Sanction.

4.	Detailed proposals of the subject / Project :

- Brief details of the scheme are as follows:-

  - Length of Road			:	3000 M

  - Width of Carriageway		:	15.80 M

  - Right of way			:	45.40 M

- The entire stretch of road between RML Roundabout and Teen Murti Roundabout has been divided into three different stretches.  The three different stretches are as follows:-

  - The stretch from Teen Murti to 11 Murti

  - The stretch from Eleven Murti to RML roundabout.

  - The stretch from wall of swimming pool to Talkatora Stadium marriage ground.

  - More green patches on Presidential Estate

  - Addition of heritage elements on the Presidential Estate side.

  - More paved area on opposite side of Presidential Estate.

  - Cycle track, shelters, benches, semi-covered spaces, pergolas.

  - Landscaping, Space for mobile vendors and Hawkers.

  - The stretch from the wall of swimming pool to the RML roundabout to be treated as a public plaza.

  - Proper lighting & clear visibility in parking to ensure safety at night.

  - Bus bays & Zebra crossing at suitable positions.

  - Proper parking space.

  - Provision of view point for 11-Murti from two ends of Sardar Patel Marg.

  - Various landscape elements with low & medium shrubs and plantations.

- Civil works

- Walkways

- Parking

- Cycle Track

- Architectural features/elements

- Street furniture items

  - Stone lamp posts

  - Cast Iron lamps posts

  - Stone Bollards

  - Stone Decorative Bollards

  - Sculptures

- Horticulture & Related works

- Grassing & Plantation

- Laying of good earth

- Sprinkler Hydrant system

- Electrical works

- Cables (different sizes)

- Feeder pillars

- Lights/ Light fixtures

- The kiosks etc. is not in scope of work & would be constructed separately as per the design approved at a later date.

5.	Financial Implications of the proposal :

The financial implications of the streetscaping/beautification of Mother Teresa Crescent works out to Rs. 9,05,35,500/-.

6.	Implementation schedule with timelines for such stage including internal processing,

- Accord of A/A & E/S			-	Sep.’08

- Preparation of Detailed Estimate		-	Oct.’08

- Call of Tender				-	Nov.’08

- Award of work				-	Dec.’08

- Execution of work			-	Jan.’09-Jun.’10

7.		Comments of the Finance Department on the subject with diary no. & date.

Finance Department has concurred the Preliminary Estimate vide diary No.1833/Finance/R-Civil dated 28 Jul.’08 subject to following:-

(a)	Availability/ adequacy of plan funds.

(b)	Sustainability/ maintainability of the items of work within reasonable cost after execution of work.

(c)	The finance department has further advised that in house expertise of architect department of NDMC be availed at the stage of according technical sanction of the scheme with a view to ensure that aesthetics of the area will not be affected adversely & Chief Architect or representative should be included in the project team as a technical hand.

8.	Comments of the Department on the comments of the Finance Department:

(a)	The funds would be asked at RE/BE stage under plan funds once the Administrative Approval is accorded by the Council as per practice in vogue.  Since a decision has been taken to streetscape the important roads in view of Commonwealth Games 2010 adequate funds would be made available.

(b)	As far as sustainability/maintainability of items of work within reasonable cost after execution of work is concerned, it is proposed to outsource the maintenance of streetscaped roads through a outsourcing agency as is being done for the maintenance and upkeep of Central Park in Connaught Place.

(c)	As per the project team constituted vide office order dated 10 May’06 a representative of CA department is a member of project team.

9.	Details of previous Council Resolution existing Law of Parliament & Assembly on the Subject:

The presentation of conceptual plan was made to the Council vide Reso. No. 09(A-51) dated 21 Nov.’07

10.	The comments of Law Department on the subject:

Law has no comments to offer.

11.		Comments of the Department on the comments of Law Department :

Nil

12.	Certification by the Department that all Central Vigilance Commission (CVC) guidelines have been followed while processing the case.

Necessary guidelines of CVC would be followed during tendering.

13.	Recommendations :

The case is placed before the Council for consideration & accord of Administrative Approval & Expenditure Sanction for Rs.9,05,35,500/- for Streetscaping of Mother Teresa Crescent.

COUNCIL’S DECISION

Resolved by the Council to accord Administrative Approval & Expenditure Sanction amounting to  Rs.9,05,35,500/- for Streetscaping of Mother Teresa Crescent.