ITEM NO. 13 (A-25)

- Name of Work:- Waste Water Management / Treatment for Reuse of Water for Hort, Purpose. S. H.:- Construction of Tertiary Treatment Plants at Lodhi Garden, Nehru Park and Talkatora Garden. (Preliminary Estimate Thereof).

- Name of the Deptt.	:  Civil Engineering, Public Health Circle,

Sewer Project Division.

- Brief History of the Subject / Project:

M/s. SNC-LAVALIN Infrastructure Pvt. Ltd. was engaged as consultant for preparation of DPRs for utilization / Treatment of unfiltered water received from DJB STP Okhla. In phase-I, the consultant has proposed the construction of TTPs for treatment of unfiltered water of capacity of existing available unfiltered water through CPWD network in three gardens. Accordingly, preliminary estimate amounting to Rs 5,11,30,000/- has been framed for construction of TTPs based on Anoxic Bioremediation (ABR) and Constructed Wetlands (CW) technology with the provision of chlorination and activated carbon filter, construction of underground storage reservoirs for storage of unfiltered water for 12 hrs detention period and construction of underground storage reservoirs for storage of treated / filtered water for 1 day detention period, at following Parks

Lodhi Garden		– 	0.45 MLD- 1 no, 0.15 MLD- 02 nos,

Nehru Park 		– 	0.15 MLD-03 nos,

Talkatora Garden 	– 	0.15 MLD-01 no.

- Detailed Proposal on the subject/project:

The proposal contained for the construction of TTPs based on Anoxic Bioremediation (ABR) and Constructed Wetlands (CW) technology with the provision of chlorination and activated carbon filter, construction of underground storage reservoirs for storage of unfiltered water for 12 hrs detention period and construction of underground storage reservoirs for storage of treated / filtered water for 1 day detention period for three major gardens, Lodhi Garden – 0.45 MLD near kothi no. 21A on Amrita Shergil lane, 0.15 MLD near glass house nursery and 0.15 MLD near gate no. 1 (opposite Mausam Bhawan). Nehru Park – 0.15 MLD near entry gate (opposite to Australian embassy), 0.15 MLD near entry gate (opposite to Pakistan embassy) and 0.15 MLD near foundation stone of Nehru Park and Gulab nursery (opposite to Serbia embassy). Talkatora Garden – 0.15 MLD near entry gate on Mother Teresa Crescent road and adjacent to boundary wall of Talkatora garden.

- Budget Provision:

There exists a budget provision of Rs 3.83 lakhs under RE for year 2011-12 and Rs 5.00 lakhs under BE for year 2012-13 under head  52.412.40.4.24.116 at page no. 362 of budget book 2012-13 Vol.2

- Implementation Schedule with Timeliness for each stage including Internal Processing:

After approval, the implementation schedule will be as under:-

Appointment of consultant for

preparation of specification/DE					10 weeks.

Technical sanction of DE	 				06 weeks.

Preparation and approval of draft NIT				06 weeks.

Call of tenders 							08 weeks

Award of work 							04 months.

The execution of works						15 months.

- Comments of the Finance Department on the Subject:

The Finance department while giving no objection to proposal of the department vide Dy. No 200 dt. 02.02.2012 observed as under:

“In another file pertaining to DPR of this project, finance has given some observations. Subject to acceptance of DPR by competent authority and decision being taken to take all the three works instead of having pilot project in the first instance, keeping the possibility of project being covered under JNNURM for entire untreated water supply system by DJB, we have no objection to the proposal of the deptt. given on P-13/N.”

- Comments of the Department on Comments of Finance Department:

DPR already accepted by the competent authority. It is proposed for AA/ES as proposed by department for providing TTPs at all the major three gardens of NDMC.

As per the advice of finance department, execution of only one TTP of 0.45 MLD capacity in Lodhi garden shall be taken up initially.

- Legal Implication of the Subject:

--Nil--

- Details of previous Council Reso. Existing Law of Parliament and Assembly on the subject:

--Nil--

- Comments of Law Department:

--Nil—

- Comments of  the department on comment  of Law Department:

--Nil--

- Certification by the Department that all Central Vigilance Commission (CVC) guidelines have been followed while processing the case.

It is certified that all the CVC guidelines have been followed.

- Recommendations:

The case is laid before the council for the consideration and accord of A/A&E/S for an amount of Rs 5,11,30,000/- for the work of “Name of Work:- Waste Water Management / Treatment for Reuse of Water for Hort, Purpose. S. H.:- Construction of Tertiary Treatment Plants at Lodhi Garden, Nehru  Park and Talkatora Garden.”

COUNCIL’S DECISION:

Resolved by the Council to accord administrative approval and expenditure sanction amounting to Rs.5,11,30,000/- for the work of “Name of Work:- Waste Water Management / Treatment for Reuse of Water for Hort, Purpose. S. H.:- Construction of Tertiary Treatment Plants at Lodhi Garden, Nehru  Park and Talkatora Garden.”

It was further resolved by the Council to first execute the above work at the Talkatora Garden as a pilot project and on evaluating its results, further projects be undertaken.