ANNEXURE – ‘A’

ITEM NO. 4(A-23)/20.09.2006

- 1.   Name of the subject/Project :

- Sub: Preservation/Restoration of  Heritage Building in NDMC area.

- SH : Façade Restoration of N.P. Boys Sr. Sec. School, Mandir Marg, N.Delhi.

- 2..    Name of the deptt./deptt. concerned :

- Civil Engg. Deptt., NDMC

- 3.    Brief History:

- N.P. Boys Sr. Sec. School and its surrounding building/structures has survived the hazards of time and provides the tangible link between the past and present giving a continuous cultural identity and is an architecturally significant, carry strong cultural overtones and being a part of cities heritage need care/conservation.  This being an essential component in a civilized society through which architectural, aesthetic, social economic, political and cultural values of the past are observed, besides it shows an architectural, aesthetic, historic of cultural values with local landmark contributing to the image and identity of the city and thus required to be restored to its old glory by preserving & restoration of the same.

- 4.    Detailed proposal on the subject/project:

- An estimate amounting to Rs. 2,02,00,000/- approx. has been framed to obtain the A/A & E/S from the Council for restoration of the front façade of the building, restoration of water proofing work, structural cracks, all sensitive historical features, repair of old masonry structure, restoration of garden, illumination of building etc. so as to have the original magnificent elevation.

- 5.    Financial implications of the proposed project/subject:

- The total financial implications of the project/subject would be Rs. 2,02,00,000/- approx.  This amount is on the basis of details submitted by an Architect Consultant appointed for Architectural & Conservation, Design Consultancy for Implementation of  Façade Restoration of N.P. Boys Sr. Sec. School, Mandir Marg, New Delhi.

- There is a budget provision of Rs. 10,00,000/-  exists under the Head of A/C H.1.8  vide item no. 281 during the  year 2006-07.

- 6.   Implementation schedule with timeliness for each stage including internal processing:

## TENTATIVE TIME SCHEDULE

| Sl.No | Stage/Activity | Time | Target date | Remarks |
| --- | --- | --- | --- | --- |
| 1. | Appointment of consultant and signing of agreement. |  |  | Completed. |
| 2. | Concept design and Report Rough cost etc. |  | 11.03.06 | Completed |
| 3. | Preliminary design, drawings incorporations of modification suggested by employer, preliminary estimates. |  | 24.04.06 | Completed |
| 4. | Submission to DUAC and Heritage Committee. |  | 31.07.06 | Permission from the Heritage Committee granted in June, 06. Drawings has been submitted to DUAC. |
| 5. | Approval by statutory body |  | 30.09.06 |  |
| 6. | Working drawings, Tender documents, Bill of Quantities, short listing of contractor, Tendering process |  | 31.12.06 |  |
| 7. | Completion of work | 54 weeks | Dec. 07 |  |
| 8. | Likely commissioning of Project in all respects |  | 31.03.08 | - |

- Comments of the Finance Deptt. on the subject:

- In view of the clarification given by the deptt. as well as recommendation of CE (C-II), we concur in the PE amounting to Rs. 2,02,00,000/- (Rs. Two Crore two lac) for the work of  Façade Restoration of  N.P. Boys Sr. Sec. School, Mandir Marg, New Delhi, subject to :-

- The estimate has been submitted by the consultant and same has been checked on their rates as such due care be taken in while submitting the detailed estimate in the Planning Division alongwith drawing.

- Correctness of data.

- Availability of funds.

- Approval of Competent Authority

- Execution of work by adhering codal provisions.

- Comments of the Department on comments of Finance Deptt.

- It is clarified as under:

- 1 & 2.      Due care shall be taken while submitting the detailed

- estimate in the Planning Division alongwith drawing etc. & its

- correctness of data &  rates.

- Sufficient funds are available.

- The case is placed before the Council for its approval.

- The work shall be got executed by adhering codal provisions.

- Legal Implication of the project:

- NIL

- 10.    Details of previous Council Resolutions, existing law of

- Parliament and Assembly on the Subject:

- NIL

- Comments of the Law Department on the subject/Project

- As no legal implication involved, hence the matter was not submitted to the Law    Deptt.

- Comments of the Department on the comments of Law Deptt.

- No Comments

- Recommendation

The case is placed before the Council for approval of the proposal  & to  accord Administrative Approval & Expenditure  sanction to the  Preliminary   Estimate amounting to Rs. 2,02,00,000/- (Rs. Two crores Two lacs only).

## COUNCIL’S DECISION

Resolved by the Council that administrative approval & expenditure sanction to the Preliminary Estimate amounting to Rs.2,02,00,000/- is accorded.

Further resolved by the Council that during the restoration of N.P. Boys Sr. Sec. School not only the façade but the strengthening of the existing buildings and problems pertaining to seepage and other constructional weaknesses would also be dealt.

- Further resolved by the Council that a presentation be made to the Council, highlighting not only façade strengthening of the existing building as well as retrofitting the building for its toilets and plugging seepages, in the next Council Meeting.