ITEM NO. 02 (A-71)

1.	Name of the subject/project

Sub:  Streetscaping of NDMC roads.

SH:   Streetscaping of Tees January Marg, Tees January Lanes &

Adjacent Round Abouts.

2.	Name of the Department

Civil Engineering Department, Road-IV Division.

3.	Brief history of the subject/project

- A decision was taken in the year 2006 to take up ten important roads for streetscaping and M/s. Oasis Design was appointed as Landscaping Consultant for a package of four roads & development of Hanuman Mandir Plaza with Tees January Marg and Lane as one of the roads taken up for streetscaping.

- Since Gandhi Smriti is located on Tee January Marg and is visited by tourists from other parts of the country and world, it was decided to beautify the roads surrounding the Gandhi Smriti i.e. Tees Januaury Marg, Tees January Lane and adjacent round abouts.

- Accordingly, as per terms of agreement Consultant submitted the    conceptual design for proposed streetscaping of Tees January Marg and Lane.  A presentation was made by M/s. Oasis Design of conceptual plan on 26th June 2006 when Chairperson, E-In-C and other NDMC Officers were present.  Conceptual plan was also shown to the President, Gandhi Smriti.  The conceptual plan of Tees January Marg and Lane was finally approved by Chairperson in Sept. 2006.

- Based on approval of conceptual plan M/s. Oasis Design has submitted details of measurement, analysis of rates alongwith preliminary estimate.

- The Empowered Committee has approved the conceptual proposal along with the Preliminary Estimate and recommended that the case be placed before council for accord of A/A & E/S with a suggestions that for irrigation purposes feasibility of two tube

wells, table top crossing and compost pit be explored.  The same will be examined and suitably incorporated at detailed planning stage.

4.	Detailed proposals of case

- Tees January Marg

The brief details of scheme are as follows: -

- Tees January Marg and approach to Tees January Marg to be redeveloped so as so to give an identity to the road and signify its importance.

- Relocation of bus parking and others parking from Tees January Marg to Tees January Lane.

- Sidewalks to be buffered from road with green strip.

- Frontage of Gandhi Smriti to be developed as Memorial Plaza with all the kiosks and vendors to be shifted from front of Gandhi Smriti to the round about in the lane.

- Main access to Gandhi Smriti proposed from Aurangzeb Road.

- Smooth paving material for sidewalks.

- Adequate lighting alongwith suitable street furniture in pedestrian plaza.

- The brief of various Civil, Electrical & Horticulture Works is as follows:-

Civil Works

- Improvement of footpath on both sides of roads.

- Creation of Plaza in front of Gandhi Smriti.

- Improvement in Drainage Works.

- Redevelopment of Rotaries (2 nos.).

  - Water Body (1 no.)

  - Development of outer segments (5 nos.)

  - Improvement in geometry of traffic islands at the junction of the rotary with the radial roads (5 nos.)

- Walkway

  - Misc. works like sculptures etc.

Horticulture & related works

  - Plantation

  - Laying of irrigation lines on both sides of road & pumps.

  - Rain water storage tanks for irrigation (2 nos.).

Electrical Works

  - Cables (different sizes).

  - Poles & pole light fittings.

  - Uplighters

(b)	 Tees January Lane behind Gandhi Smriti & National Defence College

  - The entire Tees January Lane at the rear of the Gandhi Smriti is proposed to be revitalized to house car-parking, bus parking & outdoor plaza so that the visitors to Gandhi Smriti get proper parking facilities.

  - This area is presently under utilized and has access to Gandhi Smriti from rear & is proposed as alternate entrance from the newly parking facilities.

  - The NDMC service centre next to the school in the vicinity is proposed to be shifted to the Tees January Lane behind the Defence College so as to make way for a bus-parking facility.

  - Effective circulation plan is proposed to be put in place in the    lane.

  - Round-about on the Tee January Lane is proposed to be   redesignated to house a pedestrian garden plaza.  This plaza will also house the kiosks to be shifted from the front of the Gandhi Smriti.

  - The design is proposed to have a slightly sunken plaza with the shops camouflaged within the landscape design of the Round-About.  The pedestrian plaza can act as a spill-over of the activities related to the kiosks and visitors.

  - This outdoor plaza with the kiosks will have very high level of visibility ensuring good popularity for the kiosks.

  - The car parking in front of Claridges hotel is proposed to be shifted to Tees January Lane.

  - The details of various works proposed are as follows:-

Civil Works

- Construction of Shops			:	7 nos.

- Construction of Service centres		:	2 Nos.

- Development of Parking & plaza

- Construction of toilet block & Taxi Stand :	1 No.

- Widening of service road

- Laying of irrigation lines, storage tanks & pumps.

- Poles & pole lights fittings for outdoor plaza along with related works.

- Uplighters, Bollard Lights, Flood lights.

(c) 5% of Estimated cost of civil works has been catered  for road signages, seating and shifting of services etc.,  5% for consultancy charges and 5% for provision of tree root guards, grating and other misc. works.

5.	Financial implications of the proposed subject

Estimated cost for streetscaping/beautification of Tees January Marg, Tees January Lanes and adjacent Round abouts is Rs. Rs.7,63,04,600/-.

6.	Implementation schedule with timeliness for such stage including

internal proceeding

- Accord of A/A & E/S			-	Feb.’08

- Preparation of Detailed Estimate/NIT	-	Mar.’08

- Call of Tender				-	April’08

- Award of Work				-	June’08

- Execution of work			-	July’08 to Dec.’09

7.	Comments of Finance Department on the subject

The finance department has concurred the preliminary estimate of Rs.7,63,04,600/- for streetscaping/beautification of Tees January Marg, Tees January Lanes and adjacent Round-abouts subject to the following: -

(i)	Certification by the department to the effect that the existing facilities proposed to be dismantled/replaced have actually served their useful type spam.

- Certification by the department to the effect that the specifications proposed in the estimate are in confirming with the approved specifications.

- Estimate of Horticulture work and Electrical work are duly checked by the respective department may also be annexed with PE.

- The consultation fee being more than Rs.50.00 lacs should have been approved by the Council in terms of Section 143(C) of NDMC Act, 1994. So Ex-post-facto approval of the Council may be obtained in respect of Consultation Fee payable to M/s. Oasis Designs Inc.

- The department shall ensure that the fee payable to the consultant is regulated in terms of condition No.8 of the agreement and restricted to lump sum payment of Rs.51.00 lacs only.

8.	Comments of the Department on comments of Finance Department

Comments of the department are as follows:

(i)	It is certified that the existing facilities have served their useful life span.  However, necessary credit has been considered in preliminary estimate for serviceable material to be dismantled and replaced.

(ii)	It is certified that the preliminary estimate submitted by the consultant is as per CPWD specifications and modification issued from time to time.

- The Horticulture/Electrical estimates have been checked by respective members of the Project Team/Departments.

- It was decided by Competent Authority that case be placed before council alongwith. the PE for approval.

- It will be ensured that consultancy fee is regulated as per condition 8 of the agreement and restricted to lump sum payment of Rs.51.00 lacs only.

9.	Details of previous Council Resolution

Nil.

10.	Comments of Law Department

Legal Advisor being member of Empowered Committee so no separate comments are required from Law Department.

11.	Comments of the Department on comments of Law Department

N.A.

12.	Recommendations

The case is placed before the Council for accord of Administrative Approval & Expenditure Sanction of Rs. 7,63,04,600/- for Streetscaping of Tees January Marg, Tees January Lanes, Adjacent Roundabouts and Ex-post-facto approval of consultancy fee to be paid to M/s Oasis Design for Streetscaping of roads in NDMC area.

COUNCIL’S DECISION

Resolved by the Council that administrative approval and expenditure sanction is accorded to the preliminary estimate of Rs.7,63,04,600/- for streetscaping of Tees January Marg, Teen January Lanes and adjacent roundabout as well as ex-post-facto approval of consultancy fee to be paid to M/s Oasis for streetscaping of roads in NDMC area.

Further it was decided to take necessary action in anticipation of confirmation of minutes.