ITEM NO. 23 (A-77)

- Name of the Subject/Project.

Strengthening and resurfacing of roads in NDMC area by Hot Mix Technology

- Name of Department

Civil Engineering Department, EE(RIP)

- Brief History of the Subject/Project

  - 52 roads were identified for the resurfacing with the recommendations of two consultants that were appointed for this purpose viz. Noida Toll Bridge Company Ltd. (NTBCL) and Central Road Research Institute (CRRI) and finally it was decided to carry out resurfacing of roads by Hot Mix Technology and Micro surfacing.

  - The following roads have been resurfaced using Hot Mix Technology under the tender awarded to M/s Satya Parkash Brothers Private Limited vide Council Resolution No. 12(A-16) dated 19.07.2006

- AFRICA AVENUE

- ASHOKA ROAD

- ARCHBISHOP MAKARIOS MARG

- AURBINDO MARG

- BANGLA SAHIB MARG

- DR. S. RADHA KRISHNAN MARG

- DR. ZAKIR HUSSAIN MARG

- BETWEEN OBEROI FLYOVER AND S.B. MARG CROSSING

- BETWEEN C-HEXAGON & S.B. MARG (STONE MASTIC ASPHALT)

- FEROZE SHAH ROAD

- HANUMAN ROAD

- JANTAR MANTAR

- JOR BAGH ROAD

- K.G. MARG

- MADHAV RAO SCINDIA MARG

- MADHULIMAYE MARG

- MAULANA AZAD ROAD

- MOTHER TERESA MARG

- PANDARA ROAD

- RAJPATH (HANDED OVER TO CPWD NOT RESURFACED)

- SAFDAR HASHMI MARG

- SAFDARJUNG ROAD

- SANSAD MARG

- SATYA MARG (MADHULIMAYE MARG TO NITI MARG)

- SHANTI PATH

- SOUTH END ROAD (RAJESH PILOT MARG)

- TANSEN MARG

- TEEN MURTI MARG

- TOLSTOY MARG

- UDYAN MARG

- VINAY MARG

- TILAK MARG (RESURFACED IN PLACE OF RAJPATH)

  - Additional roads resurfaced under this agreement are as follows.

- R.K. ASHARAM MARG

- SHERSHAH ROAD

- BHAI VEER SINGH MARG

- OLD R. K. ASHARAM MARG

- BABAR ROAD

- MAHADEV ROAD

- HAILEY ROAD

- GURUDWARA RAKABGANJ ROAD

- RED CROSS ROAD

- RAISINA ROAD

- TEES JANUARY MARG

  - A D.O. Letter No. 84/PA/VC/08 dated 15 Jan.’08 from Smt. Tajdar Babar, Vice-Chairperson NDMC, addressed to Chairman, has been received regarding resurfacing of C-Hexagon as the condition of roads has gone bad at various locations.

  - The C-Hexagon roads were last resurfaced in Nov. 2001 & are included in RIP Phase –II.

  - Keeping in view the condition of roads in C-Hexagon, the case was referred to CRRI for evaluation alongwith other roads of RIP    Phase-II.

  - High distress level from severe intensity to moderate has been observed by CRRI. The distress is mainly of cracking & raveling along with the some loss of surface material. The roughness index has also gone above 3000 as per report of CRRI. CRRI has recommended 50mm DBM with 40mm Bituminous concrete for these roads of C-Hexagon.

  - If separate tender is issued it will take about 3-4 months for finalization of tender for resurfacing of roads of C-Hexagon. Besides the rates likely to be quoted will be higher than the awarded rates for the RIP (Phase–I). The condition of roads will further deteriorate as the rotatory attracts huge volume of traffic from all the directions and attracts lot of tourists from within the country and abroad.

  - In the present contract of RIP (Phase-I) 40 roads have been resurfaced which include 11 additional roads and there is no further scope to accommodate roads of C-Hexagon unless Revised A/A & E/S is accorded by the Council.

  - The approx. cost of the work of resurfacing of roads of C-Hexagon works out to 331 lacs.

  - The sixth side of C-Hexagon i.e. between Akbar Road & Ashoka Road Junction Stand transferred to CPWD. Since we can’t leave out of this segment of C-Hexagon so it is proposed that the segment be also resurfaced and debit raised to CPWD. CPWD will be contacted in this regard.

  - The Administrative Approval & Expenditure Sanction amounting to Rs. 1899.42 lacs was accorded by council vide Resolution No.      5(A-6), dated 17.05.2006 and Revised Administrative Approval and Expenditure Sanction for Rs. 31,21,20,000/- vide Resolution No. 07(A-19) dated 18.07.07.

  - The tender was awarded to M/s Satya Prakash Bros. & Pvt. Ltd. at their quoted rate of 39.97% above the estimated cost, for Rs.25,55,65,251/- vide Resolution  No. 12(A-16) dated 19.07.06. Since, the amount of work to be done on roads of C-Hexagon will exceed the Administrative Approval by more than 10% so Revised Administrative Approval & Expenditure Sanction is required to be accorded by Council for resurfacing of roads C-Hexagon after completion of work.  However approval in principle is required to be given by Council to carry out the Additional work.

- Detailed Proposal on the subject/project.

The scope of work and specifications adopted in the work are as under:

  - Sealing the cracks by using hot rubberized bitumen 80/100

  - Track coat @ 0.25 Kg per sqm with bitumen emulsion complying with IS:8887-19953

  - 40mm to 50mm thick Dense Bituminous Macadam (DBM) using 60/70 grade bitumen.

  - 40mm thick Bituminous concrete (BC) as overlay, using PMB-40 grade bitumen.

  - Road marking with thermoplastic paint, applied mechanically.

- Financial implications of the proposed project/subject.

The financial implications of resurfacing of roads of C-Hexagon works out to Rs. 3,31,00,000/- which includes fee to be paid to CRRI for Third Party Quality Assurance.

- Schedule With timeliness for each stage including internal proceedings.

The work awarded to M/s. Satya Parkash & Bros. Pvt. Ltd. On 28.08.06 has been completed & 40 roads have been resurfaced under this agreement.  Agreement has been kept alive upto 31.03.2008.  About   4–6 weeks will be required to execute proposed work after approval is accorded by the Council.

- Comments of the Finance Depttt on the subject.

Finance Department has observed as:-

- In absence of revised estimate duly checked from planning no comments can be offered on revised Administrative Approval & Expenditure Sanction.

(ii)	If the proposal is for seeking approval in principle for discharging the liability already committed in excess of permissible limits of Administrative Approval & Expenditure Sanction pending approval of revised estimate by the Council.  We have no objection to this course of action.

  - Regarding C-Hexagon, the cost of work is over Rs. 3.00 crores in terms of rule 129 of GFR, tenders should be invited unless provision of Rule 129(2) of GFR are invoked owing to urgency or otherwise.  Circumstances under which course of inviting open offers for executing the work of proposed magnitude is not being opted may brought before the Council for consideration & decision.

  - Firm commitment from CPWD for reimbursement of expenditure proposed to be done in resurfacing of the portion of the roads fall in their jurisdiction may be obtained before hand.]

  - Requisite funds may be got allotted in RE 2007-08.

- Comments of the Department on comments of Finance Department.

Parawise replies are given as under:-

- Revised estimate will be prepared after the work is completed in all respects and quantities are finalized.

- Liabilities already committed by way of resurfacing of additional roads are within the permissible limit of 10% allowed on Administrative Approval for which approval in principle from Competent Authority has been accorded.

- Separate tenders for resurfacing of roads in C-Hexagon will take 3 to 4 months and rates are likely to be much higher than the quoted rate of RIP (Phase-I) due to increase in the cost of Bitumen.  The condition of roads will further deteriorate as the rotary attracts huge volume of traffic from all the directions and attracts lot of tourists from within the country and abroad.  Further CRRI has also observed high level of distress mainly cracking, and reveling and loss of surface material at several places.

- CPWD is being requested for the reimbursement of the expenditure for resurfacing of the portion on the road which falls in their jurisdiction.  If no firm commitment is received, no work will be carried on the portion between Akbar Road and Ashoka Road.

- Case for funds will be processed after accord of approval in principle by Council.

- Details of previous council Reso. Existing law of parliament and assembly on the subject.

- The Administrative Approval and Expenditure Sanction of this work was accorded for Rs. 1899.42 lacs by council vide item no. 5(A-6), dated 17.05.2006.

- Work was awarded to M/s. Satya Parkash & Bros. Pvt. Ltd., for Rs. 25,55,65,251/- vide council Resolution No. 12(A-16) dated 19.07.06

- Revised A/A & E/S was accorded by the council vide Reso. no. 07(A-19) dated 18.07.2007 for Rs. 31,21,20,000/-.

- Comments of Law Department on the Subject.

No legal issue is involved in this Agenda item & has got the concurrence of Law.

- Comments of the Department on the Comments of the Law Department.

No comments.

- Recommendations

The case is placed before Council for accord of approval in principle for the work of resurfacing of C-Hexagon Roads as additional work under existing agreement of Strengthening & Resurfacing of Roads in NDMC Area.  The Revised Estimate for accord of Revised Administrative Approval & Expenditure Sanction (second time) swill be placed before the Council after completion of work.

COUNCIL’S DECISION

Resolved by the Council that approval in principle is accorded for the work of Resurfacing of C-Hexagon roads as additional work under existing agreement of strengthening and resurfacing of roads in NDMC area.

Further resolved that the Revised estimates for accord of revised administrative approval and expenditure sanction be brought before the Council after completion of work.

It was also decided by the Council to take necessary action in anticipation of confirmation of minutes.