ITEM NO. 12 (A-30)

1.    Name of the subject / project:

Sub: Improvement / Up gradation of Talkatora Indoor Stadium

Competition venue of Boxing event CWG 2010.

Sub Head:  Providing HVAC system in proposed and existing block at

Talkatora Indoor Stadium

2. Name of the Deptt. / Deptt. Concerned:

Civil Engineering Department, NDMC

3. Brief History:

For implementation of the Common Wealth Games scheduled to be held in Delhi in 2010 and accordingly 1st meeting of core group of officers was held on 20.10.04 in the conference Room of Chief Secretary, Delhi, to select various competition & training venues. Accordingly, Talkatora Indoor Stadium & Shivaji Stadium was selected to host events during the Common Wealth Games -2010. For proper renovation of the stadias, a rough cost estimate was prepared and the case was placed before the Council to accord approval to the proposal. Council vide its Reso No. 10 (A-9) dated. 22.07.05. approved the proposal for up-gradation of NDMC stadias as under:

“Council resolved and approved the up-gradation of two NDMC Stadias to the international level even if these are not used during Common Wealth Games from its own funds at a rough cost of Rs. 30.45 crores. In case, it is decided to use the stadiums for CWG the requisite funds would come from Delhi Govt.”

The decision of the council was accordingly intimated to Jt. Director (UD), Officer-in-Charge, Co-ordination Cell, Govt. of NCT of Delhi, Department of Urban Development for arrangement of requisite funds.

Considering the above & after having detailed discussions and deliberations held with Mr. Prasad, ADG (Tech) SAI and with M/s EKS, an international consultant appointed by SAI for selection, submission of venue brief, technical parameters, examining the drawings as per requirement and make recommendations to Organising Committee, CWG on the games, selected to host Boxing a competition venue at Talkatora Indoor Stadium and a training venue Hockey Event at Shivaji Stadium. For this purpose, a need was felt for Improvement / Up gradation of Talkatora Indoor Stadium in order to meet the requirement of CWG Federation and as per the venue brief submitted by the International Consultant, M/s EKS, a new multi storey block with the two basement for parking just adjacent to the existing Talkatora Indoor Stadium is to be constructed. Addition / Alteration   to existing Stadium and Up-gradation of all services to be carried out as per concept plan.

Accordingly based on approved concept plan and as per venue brief provided by OC-CWG/ EKS HVAC system for New Block and Existing Stadium was developed and designed.

4. Detailed proposal on the subject/ project:

M/s Raja Aederi consultant Pvt. Ltd. has been appointed as an Architect Consultant for the project of Talkatora Indoor Stadium and Shivaji Stadium.

The Architect Consultant submitted the detailed estimate alongwith the drawings as per the venue brief, presentation made before the Organising committee and discussions held on the subject with the Traffic/ Security/ Delhi Fire Services. The concept / detailed proposal was subsequently approved by O.C. C.A NDMC, DUAC and Delhi Fire Services and accordingly, the detailed estimate amounting to Rs. 9,36,27,000/- was technically sanctioned and the NIT amounting to Rs.9,09,00,000/- was approved by the competent authority for Providing HVAC system in proposed and existing block at Talkatora Indoor Stadium

The tenders were invited with the last date of application, sale & receipt as 31-01-08, 01-02-08 & 06-02-08 respectively. On the request of the firm the date of opening was extended to 19.02.08. Wide publicity was made by publishing in the leading daily newspapers in Delhi and edition outside Delhi and as well as on NDMC & Delhi Govt website. In response to the above, the following three firms applied for issue of tender documents.

1. M/s Aero Comfort (P) Ltd.

2. M/s Blue Star Ltd.

3. M/s Voltas Ltd

Out of the above three applicants, all the three firms were found eligible and as such, the tenders were sold to all the three firms from the division. On the date of opening i.e. 19-02-08 only two tenders were received. The comparative statement of technical bid was prepared and both tenders were found eligible. The price bid of M/s Aero Comfort and M/s Blue Star Ltd. The eligible firms were opened on 08.05.08.

Estimated cost put to Tender; Rs. 9, 09, 00,000/-

S. No.               Agency 		  	 % age quoted             Amount

1.	  M/s Aero comfort (P) Ltd.                 38.03 % above      Rs 12, 63, 48, 200/-

2. 	  M/s Blue Star Ltd.	                       2.97 % below       Rs 8, 82, 00, 000/-

As per CPWD works manual 2007 section 19.4.3.1, if the lowest tender is less than the estimated cost put to tender +10%, there is no need of preparing justification. The overall tender amount works out to Rs.8, 82, 00, 000/- which is 2.97% below the estimated cost put to tender.

The case was sent to Finance for their concurrence in the proposal.

5. Financial implications of the proposed project/ subject:

The detail of financial status of project and tender already awarded is appended below:-

1.  A/A & E/S for whole project					=	104.01crores        (Vide reso No. D-1 (A-47) dt 5/11/07.)

2. Years wise flow of funds demanded from Govt of Delhi

2007-08 			=	10 crores

2008-09			=	70 crores

2009-10			=	24.01 crores

3.  Detail of tenders already awarded:-

- Construction of new  sports facilities block 		= 	52.98 crores

(Approved vide reso. No. D-1(A-47) dt. 5/11/07.)

b)  Addition/ Alteration of existing Stadium.			= 	19.19 crores

(Approved vide item No. 15 (A-86) dt. 31/3/08.)

c)  Fire fighting work of new and existing Stadium.		=	3.23 crores

(Approved vide item No. 03 (A-80) dt. 31/3/08.)

d) Establishing of ESS at upper basement of new block	= 	1.87 crores

(Approved vide item No. 04 (A-81) dt. 31/3/08.)

e)  Supply, Installation, Testing & Commissioning of        	=     	2 .06 crores

1000 KVA D. G Sets at Talkatora Indoor Stadium

(Approved vide item No. 11 (A-07) dt.28/04/08.)

f)  Installation of Lifts at Talkatora Indoor Stadium.   	=    	50.8 Lac

( Approved vide item No. 17 (A-25) dt. 21/5/08)

- The financial implication of this tender is Rs. 8, 82, 00, 000/-, which is processed for approval of council.

6. Implementation schedule:

Time of completion of work:		10 months

7. Comments of the Finance Department on the subject:

As the empowered committee has approved the case after due deliberation, we have no objection for placing the case before the council. The finance department approved vide diary No. 1485 dated 11/6/08.

8. Comments of the Department on comments of Finance Department:

No Comments

9. Legal Implication of the project:

NIL

10. Details of previous council Resolutions, existing law of Parliament and    Assembly on the subject:

- Reso. No. 10 (A-9) dated. 22.07-05 approved the proposal for up-gradation of NDMC stadias as under:

“Council resolved and approved the up-gradation of two NDMC stadiums to the international level even if these are not used during Common Wealth Games from its own funds at a rough cost of Rs. 30.45 crores. In case, it is decided to use the stadiums for Commonwealth Games the requisite funds would come from Delhi Govt.”

- Reso No. 01 ( A-47 ) dated 05-11-07 approved the proposal for award of work to M/s Simplex Projects Ltd., A/A & E/S amounting to Rs. 204 crores to the whole project of stadias and consultancy fee of the Architect Consultant as under:

“ Resolved by the Council that approval is accorded to the recommendation of the department, as mentioned in serial no. 1 to 3 of para 16 of the  preamble on the confirmation by the department that all CVC guidelines have been adhered to in this case.”

Department may initiate action in anticipation of confirmation of minutes.

11. Comments of the Law department of the subject / project.

NIL

12. Comments of the Department on the comments of Law department.

NIL

13.	 It is certified that all Central Vigilance Commission (CVC) guidelines have been followed while processing the case.

14. Recommendation of Department

The case is placed before the Council for award of  the above work to M/s Blue Star Pvt  Ltd at their total tendered amount of Rs 8,82,00,000/-which is 2.97%  below the estimated cost put to tender of Rs. 9,09,00,000/- The department may initiate action in anticipation of confirmation of minutes.

COUNCIL’S DECISION

Resolved by the Council to accord the work for providing of HVAC system in the proposed as well as existing blocks at Talkatora Stadium to M/s Blue Star Pvt. Ltd., at their total tendered amount of Rs.8,82,00,000/-, which is 2.97%  below the estimated cost put to tender of Rs.9,09,00,000/-.

It was also decided that the department may initiate action in anticipation of confirmation of the minutes by the Council.