ITEM NO. 04 (A-11)

1.	Name of the subject/project

Construction of 440 type-IV (Spl.) Flats at Sec.-14, Dwarka Phase-II, New Delhi.

2.	Name of the Department	:	Civil Engineering Department Zone-II

3.	Brief history of the subject/project

- Council vide Resolution No.11(A-121) dated 18.02.2009, resolved in Preliminary estimate amounting to Rs.190,01,02,000/- with a provision of 9 storied + stilt and community hall with three basements for the construction of 440 Type-IV(Spl.) Flats at Sec.-14, Dwarka Phase-II.

(b)	The proposed quarters are to be constructed on a land measuring 2.79 hectare, which was allotted to NDMC by DDA. Before taking of this project, the drawing were modified as per letter received from DDA and it was proposed with a provision of 11 stored + stilt,, community hall with three basements and an additional room for servant for each flat. Due to which FAR has been increased from 168.76 to 192.82. The cost index has been enhanced from 14% to 36%. Accordingly the Preliminary Estimate has been revised to Rs.282,24,65,000/-.

4.	Detailed proposal on the subject/project

- As per the Revised Preliminary Estimate, there is provision of 440 Type-IV flats to be constructed in 10 Nos. multistoried blocks i.e. 11 storied + stilt, community hall with three basements and additional room for servant having R.C.C. frame structure with the provision of earthquake resistance, Pile foundation for multistoried blocks and raft foundation of Community Centre, including superior specifications like vitrified tiles in floors, granite stone on top of kitchen counter, stainless steel sink, ceramic tiles in W.C, bath & kitchen and outer finish of stone cladding and item of A.P.P. on terrace with details of works Civil, Electrical and fire fighting which has been prepared to be revised as under:-

| Works | A/A & E/S Vide Reso. No. 11(A-121) dated 18.02.2009 for Rs.1,90,01,02,000/- | Revised A/A & E/S is required | Remarks |
| --- | --- | --- | --- |
| Civil Works | Rs.163,31,21,000/- | Rs.245,20,28,000/- | The A/A & E/S of RPE is required because of increase in stores, cost index on PAR 2007 and addition of room for servant with each flat. |
| Electrical Works | Rs.23,09,94,000/- | Rs.31,41,52,000/- |  |
| Fire Fighting Works | Rs.3,59,87,000/- | Rs.5,62,85,000/- |  |
| Total | Rs.190,01,02,000/- | Rs.282,24,65,000/- |  |

Provision of one additional room for servant has been considered by Chief Architect beyond authorization/scale of Type-IV.

The proposal was placed before the Council during its meeting on 20.04.2011 vide Item No.04(A-02) and deferred since the proposal was not addressing the deficiencies of Type-III accommodation. (Copy of the Resolution is annexed at Annexure I, See pages 22 - 24) The proposal is placed again for consideration after addressing the concern regarding Type-III Quarters.

Placed below at flag ‘X’ is the copy of Resolution No.  04(A-02) dt. 20.04.2011, vide which, the revised preliminary estimate in respect of above said work was placed before the Council for revised A/A & E/S for Rs. 282,24,65,000/-and the case was considered and deliberated by the Council and deferred.  In this connection, it is submitted that, earlier the preliminary estimate amounting to Rs. 190,01,02,000/- with a provisions of stilt +  9th  storied and a community hall with three basements was accorded by the Council vide Reso. No.  11(A-121) dt. 18.2.2009. The same proposal was revised for stilt + 11th storied with a provision of an additional room for servant with each flat and community hall with three basements.  Considering the enhancement in the cost index, and revised drawing based on use of available FAR, the revised administrative approval was placed before the Council and Council deferred the case since the proposal was not addressing the deficiencies of Type-III quarters. In this connection it is again submitted for consideration of the Council that the scheme is now at very advance stage and the following clearances are with us.

1.	Height clearance from Airport Authority of India.

2.	No objection certificate from Chief Fire Office of Delhi

3.	Scheme supposed to be cleared from DUAC in next meeting. Since all the issues have been deliberated and changes incorporated.

The present position of the proposal could be achieved after dedicated and concerted efforts with respective authorities in last 2-3 years.

It is, further mentioned that the land for the above said scheme was allotted to NDMC by DDA in the month of May, 1996 and the possession of the same was taken over on 10.09.1997.  As per the terms and conditions of the allotment letter, the construction as per the sanctioned plan should have been completed within a period of 2 years from the date of taking over the possession of the plot allotted,  i.e. upto 10.09.1999, which is already delayed.  The NOC from Airport Authority was issued on dt. 15.12.2008 with validity for a period of 5 years from the date of issue to construct a building, failing which, the fresh NOC from Airport authority of India will be required. The validity is likely to expire on 14.12.2013.

In view of the position explained above and keeping in view the fact that the project initially started in the year of 2007 and took almost four years to obtain clearance from the different authorities, and to save the allotment of land and to keep alive the clearance of Airport Authority of India and NOC of CFO, Delhi, it is proposed to concur the revised preliminary estimate in respect of above said scheme, considering that the allotment of the same flat will be made to the eligible employee for Type-IV flats as also to those for Type-III employees.

5.	Financial Implication of the proposed Project/Subject

On the basis of the Architectural drawings, the Preliminary Estimate amounting to Rs.282,24,65,000/- prepared on the basis of PAR-2007 duly checked by the Planning has been concurred by the Finance.

6.	Implementation schedule with time limits for such stage including internal processing.

Time of completion of the Project-4 year after the award of the work.

7.	Comments of the Finance Department on the subject

Finance vide No.683 dated 13.04.2011 has already concurred in the proposal. Finance has seen the reply of the department and offered no comments in view of the reply given by department.

8.	Comments of the Department on comments of Finance Department.

No comments in view of above.

9.	Legal implications on the subject/project.

NIL

10.	Details of previous Council Resolution existing law of Parliament and Assembly on the Subject.

(a)	P/E approved by the Council for amounting to Rs.190,01,02,000/- vide resolution no.11 (A-121) dated 18.02.2009 with a provision of 9 storied + stilt and community centre with three basements.

(b)	The Revised Preliminary Estimate for Rs.282,24,65,000/- was placed before the Council for concurrence and the same of deferred vide Reso. No.04 (A-02) dated 20.04.2011.

11.	Comments of Law Department on the subject.

NIL

12.	Comments of the Department on the comments of Law Departments.

NIL

13.	Certification by the department that all Central Vigilance Commission (CVC) guidelines have been followed while processing the case.

Certified that necessary guidelines of CVC has been followed while processing the case.

14.	Recommendations:-

The case is again placed before the Council for consideration and approval of the revised A/A & E/S for Rs.282,24,65,000/- for Construction of 440 Type-IV (Spl.) Flats at Sec.14, Dwarka, Phase-II with the condition that the NDMC staff on waiting list for Type-III flats will be as well considered for allotment.

COUNCIL’S DECISION

Resolved by the Council to accord administrative approval and expenditure sanction to the estimate amounting to Rs.282,24,65,000/- for Construction of 440 Flats at Sec.14, Dwarka, Phase-II with the condition that, out of these 440 flats, 352 flats would be earmarked for allotment in Type III category and the remaining 88 flats would be earmarked for allotment in Type IV (Special) category.

ANNEXURE - I

ITEM NO. 04 (A-02)/20.04.2011

1.	Name of the subject/project

Construction of 440 Type-IV(Spl.) Flats at Sec.-14, Dwarka Phase-II, New Delhi.

2.	Name of the Department  :  	Civil Engineering Department Zone-II

3.	Brief history of the subject/project

(a)	Council vide resolution no.-11(A-121) dated 18.02.2009, resolved in Preliminary estimate amounting to Rs.190,01,02,000/- with a provision of 9 storied + stilt and community hall with three basements for the construction of 440 Type-IV(Spl.) Flats at Sec.-14, Dwarka Phase-II.

(b)	The purposed quarters are to be constructed on a land measuring 2.79 hectare which was allotted to NDMC by DDA. Before taking of this project the drawing were modified as per letter received from DDA and it was proposed with a provision of 11 storied + stilt , community hall with three basements and an additional room for servant for each flat.  Due to which FAR has been increased from 168.76 to 192.82. The cost index has also been enhanced from 14% to 36%.  Accordingly the Preliminary Estimate has been revised to Rs.282,24,65,000/-.

4.          Detailed proposal on the subject/project

(a)	As per the Revised Preliminary Estimate, there is provision of 440-type –IV to be constructed in 10 Nos. multistoried blocks i.e. 11 storied + stilt, community hall with three basements and additional room for servant having R.C.C. frame structure with the provision of earthquake resistance, Pile foundation for multistoried blocks and raft foundation for Community Centre, including superior specifications like vitrified tiles in floors, granite stone on top of kitchen counter, stainless steel sink, ceramic tile in W.C, bath & kitchen and outer finish of stone cladding and the item of A.P.P. on terrace with details of works Civil, Electrical and fire fighting which has been prepared to be revised as under:-

| Works | A/A & E/S Vide Reso. No. 11(A-121)dated 18.02.2009 for Rs.1,90,01,02,000/- | Revised A/A & E/S is required | Remarks |
| --- | --- | --- | --- |
| Civil works | Rs.163,31,21,000/- | Rs.245,20,28,000/- | The A/A & E/S of RPE is required because of increase in stories, cost index on PAR 2007 and addition of room for servant with each flat. |
| Electrical works | Rs.23,09,94,000/- | Rs.31,41,52,000/- |  |
| Fire Fighting works | Rs.3,59,87,000/- | Rs.5,62,85,000/- |  |
| Total | Rs.190,01,02,000/- | Rs.282,24,65,000/- |  |

Provision of one additional room for servant has been considered by Chief Architect beyond authorization/scale of type-IV.

5.	Financial Implication of the proposed Project/Subject.

On the basis of the Architectural drawings, the Preliminary Estimate amounting to Rs.282,24,65,000/- prepared on the basis of PAR-2007 and DSR-2007 duly checked by the Planning has been concurred by the Finance.

6.	Implementation schedule with time limits for such stage including internal processing.

Time of completion of the Project-4 years after the award of the work.

7.	Comments of the Finance Department on the subject

Finance vide no.-683 dated 13.04.2011 has concurred in the proposal.  Finance has seen the reply of the department and offered no comments in view of the reply given by department.

8. 	Comments of the Department on comments of Finance Department.

No comments in view of above.

9.	Legal implications on the subject/project

NIL

10.	Details of previous Council Resolution existing law of Parliament and Assembly on the Subject.

P/E approved by the Council for amounting to Rs.190,01,02,000/- vide resolution no.11(A-121) dated 18.02.2009 with a provision of 9 storied + stilt and community centre with three basements.

11.	Comments of Law Department on the subject.

NIL

12.	Comments of the Department on the comments of Law Departments.

NIL

13.	Certification by the department that all Central Vigilance commission (CVC) guidelines have been followed while processing the case.

Certified that necessary guidelines of CVC have been followed while processing the case.

14.	Recommendations :-

The case is placed before the Council for consideration and approval of the revised A/A & E/S for   Rs.282,24,65,000/-  for   Construction  of   440   Type-IV(Spl.) Flats  at Sec.-14, Dwarka

Phase-II.

COUNCIL’S DECISION

Deferred.