ITEM NO.3 (A-38)

1.	Name of the subject/ Project:

Redevelopment of Connaught Place – Improvement of Pedestrian Area on 	Outer side of Outer Circle including improvement of subways.

2.	Name of the department/ departments concerned:

Civil Engineering Department.

3.	Brief history of the subject/project:

Connaught Place is an important & most visible symbol of Lutyen’s Delhi. The Complex was designed & developed as the Central Business district. All major services like water supply, sewer, storm water drains and power cables were laid along middle circle. To meet ever increasing demands of shopkeeper, extensive parking areas were created all along inner, middle, outer circle and the radials, power demands also shot up requiring installation of additional sub-stations. Extensive telephone connections by Telecom department also added to the maze of cables wires of TV, Internet etc.  All these development have put the Connaught Place & its merinos under lot of pressure. Public amenities are generally poor & lacking in Inner as well as Outer circle. In the year 2002, DMRC amended plans to build Metro rail corridors with an underground inter change station under Central Park & Connaught place. This had encouraged large number of visitors to come to Connaught Place. Meanwhile Delhi has offered to host Commonwealth Games-2010 which would also require major improvements to be carried out in the prestigious shopping center.

- NDMC has taken up the Redevelopment Plan of Connaught Place.  The Redevelopment of Connaught Place mainly consists of Restoration of façade of all the blocks, circulation plan, parking lots, Augmentation/upgradation of Engineering services, pedestrian plaza, new subways & improvement of existing subways.

- The subject work is a part of overall Redevelopment Plan of Connaught Place and it was decided to take up the Improvement of pedestrian area in outer-side      of outer circle including improvement of subways as the condition of walkway/footpath in this area is very bad.

- Accordingly M/s EIL was asked to prepare the plan for development of this area as a part of improvement/upgradation of Engineering services in Connaught Place.  M/s EIL after studying the existing site conditions and proposed Redevelopment Plan has prepared Preliminary Estimate for improvement of pedestrian area on outer side of outer circle including improvement of existing subways.  M/s EIL has submitted details of measurement, analysis of rates alongwith Preliminary Estimate.

4.	Detailed proposals of the case

There are four major segments in outer side of outer circle i.e. ‘P’ block, Regal  	Cinema Building, Scindia House and rest of the area. The main features of this 	improvement plan are as follows:-

- Development of Pedestrian Plaza in front of ‘P’ block, Scindia House & Regal Cinema Building & walkway in rest of the area.

- Improvement in Geometry of road section in outer side of Outer circle as well as rotaries etc.

- Provision of combination of Mandana & Granite Stone in pedestrian plaza flooring.

- New design of kerb stone of size 300X150X300 with chamfering on the outside face.

- Provision of planters, seating benches and stone railing in pedestrian plaza.

- Pedestrian area illumination and landscaping elements.

- Removal of parking adjoining ‘P’ block and Scindia House.

- Following improvements to existing subways have also been proposed at Sansad Marg, B.K.S. Marg, Janpath, K.G. Marg & Super Bazar.

- Improvement in Entry/Exit.

- Improvement of flooring & illumination.

- Civil works for provision of Escalators.

- Provision of toilets & drinking water facilities.

- The RCC duct has been proposed for laying various services like electrical cables, telecommunication cables & water supply lines etc. to avoid frequent digging of footpath.

- Wherever the ducts are crossing the radials the trenchless technology is proposed to be used to lay the pipes/cables etc.

- The electrical works include

- Provision of road lighting with improved illumination.

- Pedestrian Plaza lighting.

- Improvement in subway lighting.

- New feeder pillar boxes using stainless steel.

- 15% of the estimates have been catered for unforeseen factors like shifting of underground services etc. the quantification of which can not be done at this stage.

- For improvement of Geometrics of road in certain sections, railway land will have to be acquired which is about 570 SM.

5.	Financial implications of the proposed project/subject:

Estimated Cost for Improvement of pedestrian area of out-side of Outer Circle including improvement of subways is Rs.30,92,68,000/-.

6.	Implementation Schedule with timelines for each stage including internal processing.

- Accord of A/A & E/S				:	Jan.07

- Preparation of Detailed Estimate/NIT		:	Feb.07

- Call of Tenders					:	March 07

- Award of Work					:	April 07

- Execution of work					:	May 07 to Jan.08

7.		Comments of the Finance Department on the subject.

Finance Department has agreed to the Preliminary Estimate of Rs. 30,92,68,000/-

- Comments of the Department on comments of Finance Department.

No comments in view of concurrence of Finance Department.

9.	Details of previous Council Resolution, existing law of Parliament and Assembly on the subject.

The overall project proposals/report to carry out the Redevelopment of Connaught Place was approved vide Agenda No. 4(A-24) dated 13.02.2006 by the Council.

10.	Comments of the Law department on the subject/project.

Not applicable.

11.	Comments of the Department on the comments of Law Department.

Not applicable.

12.	Recommendations.

The case is laid before the Council for consideration & accord of A/A & E/S of Rs. 30,92,68.000/- (Rupees Thirty Crores Ninety Two lacs & Sixty Eight Thousand Only) to the Preliminary Estimate for the work of Improvement of Pedestrian Area at outer side of outer circle including Improvement of Subways.

COUNCIL DECISION

Resolved by the Council that administrative approval and expenditure sanction to the Preliminary Estimate amounting to Rs.30,92,68,000/- is accorded for the work of improvement of Pedestrian area at outer circle including improvement of subways.